## TM_Application (hidden)
Left | Top | Right | Bottom | Ref

## Cover Page
|  |  |  | Application No | 1
|  |  |  | Date of submission | 2009-11-04
|  |  |  | MIS Code | 902020
(to be filled in by the JTS)
APPLICATION FORM
EUROPEAN TERRITORIAL COOPERATION PROGRAMME
GREECE -ITALY 2007-2013
The excel protection must not be removed
Damaged application forms will be deemed ineligible
1st |  | CALL FOR PROPOSALS
Form to be filled in and returned to the following address: Joint Technical Secretariat
ETCP “GREECE – ITALY 2007 – 2013”
Balkan Center, Building D, Elevator 2, 3rd floor
9th Km Thessaloniki - Thermi Road
570 01, Thessaloniki, Greece
| Project title |  | Development of sustainable biogas strategies for integrated agroindustrial waste management
| Project acronym |  | BioGAIA

## Project_Identification
SECTION A - PROJECT IDENTIFICATION
| Project title |  |  | Development of sustainable biogas strategies for integrated agroindustrial waste management
| Project acronym |  |  | BioGAIA
[6 empty] | 2011-11-01 |  |  |  |  | 2013-10-31
| Project duration |  |  |  | Start |  |  |  | End | [5 empty] | Total Months |  | 24
| Priority Axis |  |  | 3. Improving the quality of life, protection of the environment and enhancement of social and cultural cohesion
Specific Objective |  |  |  | 3.2. Valorisation & improvement of joint protection, management of natural resources, natural and technological risks’ prevention
Brief Description of the Project
Background, objectives, partnership, main activities and expected outputs, added value
The maximum total number of characters is 3000
| (please do not exceed 1000 characters in each box) | [12 empty] | Number of characters |  |  |  | 2916
Anaerobic digestion (AD) is a process of increasing interest as a method for producing biogas from various biomass sources. Biogas has been evaluated as one of the most energy-efficient and environmentally beneficial technology for bioenergy production (Fehrenbach et al. 2008). It can drastically reduce GHG emissions compared to fossil fuels by utilization of locally available resources. The digestate is an improved fertilizer in term of its availability to crops which can substitute mineral fertilizer. The European energy production from biogas reached 6 million tons of oil equivalents (Mtoe) in 2007 with a yearly increase of more than 20% (EurObserv’er 2008). All the cross-border areas in Greece and Italy are facing today tremendous environmental problems due to pollution from agroindustrial activities (olive-mills, cheese factories etc) because of their seasonal character and their spatial heterogeneity.
Although numerous waste and byproduct recovery processes have been introduced, AD has a unique and integrative potential, simultaneously acting as a waste treatment and recovery process. AD has a great number of advantages: low nutrient requirements, energy savings, generation of low quantities of sludge, excellent waste stabilization, production of biogas and/or hydrogen. The BioGAIA project aims to capitalize on the knowledge and the experience gained during the past few years from extensive research both at the laboratory level as well as via the construction and operation of a pilot plant in the Former Prefecture of Achaia (Greece) in the framework of INTERREG IIIA (AGROENERGY project) where the efficiency of AD of selected agroindustrial wastewaters that are seasonally and locally produced was successfully demonstrated. The objective of the proposed BioGAIA project is to increase the biogas productivity in AD plants that normally treat mixtures of wastewaters based on their
seasonal availability and thus operate for periods with mono-substrates, e.g. cheese whey in Italy or cow manure in Greece during summer, to co-digest other agroindustrial wastes or agro-residues available in the area in order not only to operate efficiently but at the maximum of their operational capacity throughout the year. Therefore, the BioGAIA project targets to increase the sustainability of such AD plants and convert them from waste treatment plants into biogas (bioenergy) production plants attractive for green entrepreneurs by efficiently combining the most appropriate agroindustrial wastes (of liquid or solid form) that are available in each partner area. The goal is dual in this cross-border joint action: protect the environment using AD while, at the same time, exploit the wastes’ energy content and the constructed plants in the most efficient and productive way in terms of energy (both electrical and thermal) and material production (digestate to be used as fertilizer).
Partner Information
| Partner No |  | Partner Institution (Full Name) | [9 empty] | Country |  |  | NUTS III | Legal Status
| LP (P1) |  | University of Patras - ELKE | [9 empty] | Greece |  |  | Prefecture of Achaia | governed by public law
| P2 |  | Development Enterprise of Achaia | [9 empty] | Greece |  |  | Prefecture of Achaia | governed by public law
| P3 |  | Development Agency of Etoloakarnania Prefecture (ANAIT) S.A. | [9 empty] | Greece |  |  | Prefecture of Aitoloakarnania | governed by public law
| P4 |  | Region of Epirus - Former Prefectures of Preveza and Arta | [9 empty] | Greece |  |  | Prefecture of Ioannina | Public
| P5 |  | Region of Ionian Islands - Former Prefecture of Kefallinia & Ithaki | [9 empty] | Greece |  |  | Prefecture of Kerkyra/Corfu | public
| P6 |  | Laser Center | [9 empty] | Italy |  |  | Province of Bari | governed by public law
| P7 |  | Province of Bari | [9 empty] | Italy |  |  | Province of Bari | public
| P8 |  | 0 | [9 empty] | 0 |  |  | 0 | 0
| P9 |  | 0 | [9 empty] | 0 |  |  | 0 | 0
| P10 |  | 0 | [9 empty] | 0 |  |  | 0 | 0
Budget Per Partner
| Project Partner No |  | Country |  | Eligible Programme area
[5 empty] | ERDF (1) |  | % | National Co-financing (2) | % | Total (3)=(1)+(2)
| LP (P1) |  | Greece |  | 307500 |  | 75 | 102500 | 25 | 410000
| P2 |  | Greece |  | 101250 |  | 75 | 33750 | 25 | 135000
| P3 |  | Greece |  | 86250 |  | 75 | 28750 | 25 | 115000
| P4 |  | Greece |  | 139500 |  | 75 | 46500 | 25 | 186000
| P5 |  | Greece |  | 86250 |  | 75 | 28750 | 25 | 115000
| P6 |  | Italy |  | 315000 |  | 75 | 105000 | 25 | 420000
| P7 |  | Italy |  | 18750 |  | 75 | 6250 | 25 | 25000
| P8 |  | 0 |  | 0 |  | 75 | 0 | 25 | 0
| P9 |  | 0 |  | 0 |  | 75 | 0 | 25 | 0
| P10 |  | 0 |  | 0 |  | 75 | 0 | 25 | 0
| TOTALS |  |  |  | 1054500 |  | 75 | 351500 | 25 | 1406000
Budget & Partners per country
| Country |  | Number of partners |  |  |  |  | ERDF |  |  |  | National Co-Financing |  |  |  |  | Total
| GREECE |  | 5 |  |  |  |  | 720750 |  |  |  | 240250 |  |  |  |  | 961000
| ITALY |  | 2 |  |  |  |  | 333750 |  |  |  | 111250 |  |  |  |  | 445000
| TOTALS |  | 7 |  |  |  |  | 1054500 |  |  |  | 351500 |  |  |  |  | 1406000
Project Budget
| ERDF |  |  |  | 1054500
| National co-financing |  |  |  | 351500
| Total Budget |  |  |  | 1406000
| Project title |  |  | Development of sustainable biogas strategies for integrated agroindustrial waste management
Project Budget
| ERDF |  |  |  | 1054500
| National co-financing |  |  |  | 351500
| Total Budget |  |  |  | 1406000
Lead Partner Confirmation
By signing the Application Form the Lead Partner hereby confirms that
­ the project has not neither will receive any other EU funding (except for the funding indicated in this Application form) during the whole duration of its implementation.
­ the project is in line with the relevant EU and national legislation and policies of the countries involved.
­ all partners in the partnership receiving funding from the programme are eligible bodies as defined in the programme
­ all partners described in Section C of the Application Form are committed to taking part in the projects’ activities
­ the information is accurate and true to the best knowledge of the Lead Partner
The project budget and costs are in line with the limits set in the Call for proposals
| Signature of the Lead Partner | [9 empty] | Official Stamp of the Lead Partner's Institution if available
| Name of the signatory | [5 empty] | Prof. Dimitrios L. Kalpaxis
| Title of the signatory | [5 empty] | Vice-Rector of Strategic Research Planning and Development
| Lead Partner's Institution | [5 empty] | University of Patras
Date of signature

## Detailed Description
SECTION B - DETAILED DESCRIPTION
B.1 PROJECT IDENTIFICATION
Brief History of the Project
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1829
This project emerged from the collaboration between the Former Prefecture of Achaia, University of Patras, Former Prefectures of Kefallinia, Leykada and Preveza from Greece, Province of Bari and Centro Ricerche of Bonomo from Italy as part of the European Community Initiative INTERREG IIIA Greece-Italy 2000-2006 (financed under the European Regional Development Fund-ERDF), project “AGROENERGY” (Code No I3101004), in which we investigated the fermentative methane production from agroindustrial wastewaters, namely olive mill wastewaters, cheese whey wastewater and liquid cow manure. The lab-results obtained from the AGROENERGY project were pretty encouraging since they proved that continuous methane production from these kinds of wastewaters is feasible and stable. A pilot plant was constructed by the Former Prefecture of Achaia in the Industrial Zone of Patras (Greece) to be used for process scale-up and pilot testing of the available agrowastes within the regions involved.
Due to the limited duration of the AGROENERGY project (1 year) only demo runs were made in this pilot plant using exclusively Greek wastewater mixtures due to lack of time. The proposed project is envisaged to be a continuation of AGROENERGY that will improve the waste management status in the cross-border area of Greece-Italy andd foster renewable energy production and material recovery by exploiting their organic agro-wastes. Part of the existing infrastructure that will be utilized in the framework of BIOGAIA along with the experimental tools developed and tested within the AGROENERGY will help to capitalize the gained knowledge and forward it to a transnational level contributing to promote innovative actions towards environmental protection and also provide the basis for sustainable economic development in Greece and Italy.
Background of the project (problems/target groups/challenges to be addressed)
The maximum total number of characters is 4500
| (please do not exceed 1500 characters in each box) | [8 empty] | Number of characters | 2954
Agro-industries are major contributors to the worldwide industrial pollution problem, Greece and Italy cross-border areas being no exception. With the tremendous pace of technology development, substantial research is devoted to cope with wastes of ever increasing complexity generated by agro-industries. Therefore, agro-industries more than any other industrial sectors in this field require a dynamic and comprehensive approach for appropriate waste management. Industries processing agricultural raw materials such as various fruits, vegetables, meat, milk e.t.c. generate millions of tons of wastes and large amounts of by-products, which are totally unexploited and the absence of environmental management is significantly dangerous for the environment. These production facilities are usually scattered throughout the countryside and the raw materials processed are produced at a seasonal rate resulting thus to wastes varying significantly during the year both in quantity and characteristics.
In the agricultural sector, methane recovery and use as a clean energy source via anaerobic digestion can be a highly sustainable solution, contributing to a number of environmental objectives as well as providing social and economic benefits for rural communities. Anaerobic digestion can contribute substantial solutions both in energy generation as well as in environmentally sound byproduct recovery and waste treatment. Due to its integrative potential, in the long run it could become a key technology acting as a precursor for sustainable development. Although being state-of-the-art in sewage sludge and anaerobic industrial waste water treatment, only a few applications of anaerobic digestion of organic waste reclamation can be found in agriculture and even less in the south Italy and Greece.
Co-digestion of organic wastes is a technology that is increasingly being applied nowadays for simultaneous treatment of several solid and liquid organic wastes, in which the content of nutrients can thereby be balanced, and the negative effect of toxic compounds (e.g. phenols) on the digestion process may be decreased giving thus an increased gas yield from the biomass. Moreover, co-digestion contributes to a more efficient use of AD reactors and cost-sharing by processing multiple waste streams in a single facility as proved in the ΙΝΤΕRREG project AGROENERGY. However even in these cases there are periods e.g summer that such an AD plant is operating only on mono-substrate either for example cow manure (in Greece) or cheese whey (in Italy) at low inflow rate just to maintain the viability of the system throughout the year. In these cases, particularly when cheese whey is used alone instability problems may occur due to extensive acidegennesis, whereas a proper selection and addition of available agro-wastes in solid or liquid form may lead to a serious enhancement of biogas production and increase substantially its viability.
Objectives of the Project
The maximum number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1737
The objective of the BioGAIA project is to increase the biogas productivity in AD plants that normally treat mixtures of wastewaters based on their seasonal availability and thus operate for periods with mono-substrates to co-digest other agroindustrial wastes or agro-residues available in the area in order not only to operate efficiently but at the maximum of their operational capacity throughout the year. The BioGAIA project targets to increase the sustainability of such AD plants and convert them from waste treatment plants into biogas production plants attractive for green entrepreneurs by efficiently combining the most appropriate agroindustrial wastes that are available in each partner area. The goal is dual in this cross-border joint action: protect the environment using AD while, at the same time, exploit the wastes’ energy content and the constructed plants in the most efficient and productive way in terms of energy (both electrical and thermal) and material production.
Specific project objectives include: 1. Determination of accurate energy balances for selected types and mixtures of agrowastes based on their seasonal and spatial availability 2. Determination of anaerobic degradation rates and ultimate methane yield of selected types of agrowastes and mixtures thereof, in pilot plant scale. 3. Assessment of advantages and limitations of co-digesting different agrowastes. 4. Encouraging actions (best practices exchange, communication campaigns) aimed at supporting the development of a renewable energy culture based on gaseous biofuels frοm agro-wastes and other organic residues. 5.Increase access of stakeholders to pilot plant operation data and local sources of financing for Renewable Energy.
Expected Outputs (tangible and visible results or products relating to project activities)
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1990
The proposed project is planned to produce concrete results to alleviate the hesitations and barriers raised by stakeholders regarding the exploitation of agroindustrial wastes for electric and thermal energy as well as material recovery through a well-planned combination of engineering process development activities that will be selectively demonstrated at pilot scale. Specifically, the project aims at providing: - demonstration of a complete prototype pilot plant for the integrated management of agroindustrial wastes (in Bari), which in combination with the one already built in Achaia may prove substantial poles for attracting the interest of green enterpeneurs both Greek and Italian. - optimum operating strategies of the pilot plant towards the maximization of energy exploitation throughout a year by proper selection of available agro-wastes - optimum processes for aerobic composting or vermicomposting of digested material along with other available agrowastes in order to produce
compost of the higher compost of the higher quality according to European specifications - experimental data for the production of water adequate for irrigation either using membranes or membrane bioreactors of the anaerobically digested wastes. - all required studies for supporting the dissemination and after-life of project results (technoeconomic analysis of pilot scale results along with concrete exploitation businness plans) capitalizing the knowledge gained via previous INTERREG project (AGROENERGY) - increase the awareness of the public, local stakeholders, students and potential investors in the thematic environmental issue that is being confronted by the specific project methodology - to participating public bodies (2 Regions in Greece and the Province of Bari) the demonstration plants - in both Greece and Italy - and the tools to apply environmental laws effectively and at the same time profitably to all stakeholders facing environmental problems with agrowastes.
Expected Results (direct and immediate effects resulting from the project)
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1832
The expected results from the project implementation include: a) The pilot plant prototype that will be commissioned in this project will have a significant positive environmental contribution affecting around 2200000 inhabitants on the cross-border Greece - Italy area of the programme call because of the integrated approach in the management of several types of waste streams. Indicatively, it will be able to treat: • Agro-industrial wastes, wastewaters and combination of them. • Agricultural residues- and energy crops. b) The potential to recover electrical and thermal energy from agroindustrial wastes with a very efficient and ecological technology c) The proposed process is not a complex technological infrastructure and will present considerable energetic costs with a low carbon footprint. d) Maximizing the cost effective production of biogas, the environmental benefits from the use of anaerobic digestion and its products, the potential of anaerobic
digestion to reduce the carbon footprint of the food supply chain, the opportunity for the injection of biomethane into the gas grid and the potential of anaerobic digestion to reduce the carbon footprint of wastewater treatment infrastructure. e) This project will allow the facility to recycle and reuse the treated aqueous effluent instead of relying on other sources of process water such as rivers, groundwater wells, or purchasing potable water from the municipal grid and achieve “Zero Discharge“ system. f) The electricity efficiency is higher in anaerobic digestion of organic waste in this system than in incineration. g) Development and implementation of processing control strategies using decision support systems to maximize biogas production. h) Identification of novel process designs that will help overcome known problems of digester stability.
B.2 METHODOLOGICAL APPROACH
Project Methodology
The maximum total number of characters is 3000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 2888
The main objective of the BioGAIA project is to extent the results of AGROENERGY aiming at increasing the biogas productivity in AD plants that normally treat mixtures of wastewaters in order to substantially improve their viability beyond the level proven in the AGROENERGY project (about 4,5 years pay-back time without external co-funding). Like this these plants will transform from just waste treatment plants into profitable investments attracting the interest of green entrepreneurs and not only stakeholders that are currently involved in the agroindustrial activities and simply face the problem of waste management. To this end, both Greek and Italian partners will conduct short term surveys in order to estimate available sources of agroindustrial wastes (grape marks and tissues from grape production), agricultural residues (e.g. potatoes, oranges), industrial by products of high organic strength (e.g. glycerol from biodiesel plants) that are available in the region of each partner.
Quantitive data on these waste sources will be assessed by each Region in Greece and the Province of Bari (Italy) while their physicochemical characteristics will be estimated exclusively in the laboratory of Upatras as well as their capacity for biogas production (by running anaerobic tests like BMP-methanogenic methane potential). Based on these results the most appropriate substrates will be selected for further evaluation in lab and pilot scale. This includes the assessment of lab-scale reactors performance (using the already installed reactors plus 1 or 2 new ones). These reactors are of two-phase (acidogenic followed by methanogenic) and will be operated in co-digestion mode (using the mono-substrate that corresponds to each parner e.g cow or pig manure for greek partners and cheese whey for the Italian ones along with one or more of the selected organic wastes per region). The obtained lab results and strategies will be used for the selection of scenarios that
will be tested in the pilots (the existing Greek one and the new Italian commissioned by BioGAIA). Besides the anaerobic experimentation, the most appropriate technology will be selected for post anaerobic effluent treatment using either aerobic SBR, membranes (Ultra-, nano-, RO) either alone or in combination with the SBR). The produced excess sludge in both pilots will be tested for compost production using the aerobic conventional process or vermicomposting which also contributes to the production of an added value product that increases the plant revenues. All obtained results will be assessed technicoeconomically and exploitation business plans will be developed by each partner to be further disseminated by various publicity measures in both electronic and printed form. Management will be implemented by each partner separately (on a local level) as well as centrally by the Leader Partner.
Roles - Tasks of Partners
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1983
University of Patras (Upatras) is the Leader Partner having the responsibility for effective coordination of project activities both from managerial and scientific point of view. The consortium of BioGAIA partnership also includes 3 Regions from Greece (namely Achaia (NEA), Aitoloakarnania (ANAIT), Preveza & Arta and Kefallinia) and 2 partners from Italy, i.e. a research center (CL) and the Province of Bari (PB). Upatras will provide to all partners the instructions regarding the type of agrowastes that each one of them will try to assess in its region (in terms of available types and quantities). All characterization tests of available agrowastes (both in Greece and Italy) as well as the laboratory tests regarding the selection of the most efficient agrowastes that will boost biogas production will be carried out by Upatras. Upatras will provide technical specifications to CL for the pilot plant commissioning and supervise its installation and operation during its startup.
Upatras will have the scientific supervision on all the pilot scale tests that will run in both Greece and Italy. Will provide to all partners examples on technoeconomic analysis and exploitation plans in each partners region. Greek partners and CL will be responsible for the collection of data regarding agrowastes produced in their region, selection of representative samples from each type of agrowaste and transfer of these samples to Upatras for characterization. Each Greek partner will have the responsibility to transfer to the Greek pilot plant (ownership of NEA) adequate quantities of the selected agrowastes to run pilot tests under to supervision and guidance of Upatras. CL will commission a new pilot in order to run Italian agrowaste mixtures. Each Greek partner and CL will develop an exploitation business plan for its region based on the technicoeconomic analysis provided by Upatras. Greek partners and PB will also organize all information material and publicity measures.
Work Packages / Actions
| WP/ Action Code |  |  |  | WP/ Action Title |  |  | Start | End | Cost
| WP 1 |  |  |  | Management & Coordination |  |  | 2011-11-01 | 2013-10-31 | 194523
| Action 1.1 |  |  |  | Preparation Activities |  |  | 2010-01-01 | 2011-07-15 | 8704
| Action 1.2 |  |  |  | Project Management |  |  | 2011-11-01 | 2013-10-31 | 40113
| Action 1.3 |  |  |  | Financial Monitoring |  |  | 2011-11-01 | 2013-10-31 | 93665
| Action 1.4 |  |  |  | Project Coodination & Evaluation Meetings |  |  | 2011-11-01 | 2013-10-31 | 52041
| Action 1.5 |  |  |  | Title |  |  |  |  | 0
| WP 2 |  |  |  | Information & Publicity |  |  | 2011-11-01 | 2013-10-31 | 219817
| Action 2.1 |  |  |  | Development of Communication Plan |  |  | 2011-11-01 | 2011-11-30 | 21800
| Action 2.2 |  |  |  | Creation of Information Material |  |  | 2013-06-01 | 2013-08-31 | 48037
| Action 2.3 |  |  |  | Development of Website |  |  | 2011-12-01 | 2013-09-30 | 22712
| Action 2.4 |  |  |  | Publicity Measures |  |  | 2012-10-01 | 2013-10-31 | 51788
| Action 2.5 |  |  |  | Conferences and Training staff activities |  |  | 2013-04-01 | 2013-10-31 | 75480
| WP 3 |  | Title |  | Laboratory Supporting Actions |  |  | 2011-11-01 | 2013-08-31 | 332860
| Action 3.1 |  |  |  | Sources & Characterization of Agro-wastes. |  |  | 2011-11-01 | 2012-02-29 | 91260
| Action 3.2 |  |  |  | Commissioning of Supporting Equipment |  |  | 2011-11-01 | 2012-03-31 | 187500
| Action 3.3 |  |  |  | Performance Evaluation & Mathematical Μodels |  |  | 2012-01-01 | 2013-08-31 | 34000
| Action 3.4 |  |  |  | Lab-scale Anaerobic Effluent Post-treatment |  |  | 2012-04-01 | 2013-05-31 | 20100
| Action 3.5 | [8 empty] | 0
| WP 4 |  | Title |  | Pilot Scale Studies |  |  | 2011-11-01 | 2013-08-31 | 485300
| Action 4.1 |  |  |  | Design and Commissioning of Italian Pilot Plant |  |  | 2011-11-01 | 2012-03-31 | 229270
| Action 4.2 |  |  |  | Operation of Pilot with Basic Italian Scenarios |  |  | 2012-04-01 | 2012-12-31 | 28750
| Action 4.3 |  |  |  | Greek & Italian Mixtures for Advanced Biogas Performance |  |  | 2011-12-01 | 2013-08-31 | 94315
| Action 4.4 |  |  |  | Pilot-scale Anaerobic Effluent Post-treatment |  |  | 2013-05-01 | 2013-08-31 | 53115
| Action 4.5 |  |  |  | Composting of sludges from Greek & Italian pilots |  |  | 2012-04-01 | 2013-08-31 | 79850
| WP 5 |  | Title |  | Exploitation Business Plans |  |  | 2013-07-01 | 2013-09-30 | 173500
| Action 5.1 |  |  |  | Technoeconomic evaluation of Pilot-scale results |  |  | 2013-07-01 | 2013-08-31 | 41000
| Action 5.2 |  |  |  | Development of Exploitation Business Plans |  |  | 2013-08-01 | 2013-09-30 | 132500
| Action 5.3 | [8 empty] | 0
| Action 5.4 | [8 empty] | 0
| Action 5.5 | [8 empty] | 0
| WP 6 |  | Title |  | Title |  |  | 0 | 0 | 0
| Action 6.1 | [8 empty] | 0
| Action 6.2 | [8 empty] | 0
| Action 6.3 | [8 empty] | 0
| Action 6.4 | [8 empty] | 0
| Action 6.5 | [8 empty] | 0
[8 empty] | 2011-11-01 | 2013-10-31
Deliverables
| Action No |  | Deliv. No |  | Deliverable Title | Partner No | Partner's Contribution to Deliverable
| 1.1 |  | 1.1.1 |  | Project proposal | LP | LP collected all relevant information from the partners and prepared the project proposal
| 1.2 |  | 1.2.1 |  | Interim and the Final report (Technical & Financial reports) | LP | LP collects all relevant information from partners regarding technical and financial progress and prepares the reports
| 1.3 |  | 1.3.1 |  | 8 Progress Reports | LP | LP collects all relevant information from partners regarding financial progress and prepares the reports
| 1.4 |  | 1.4.1 |  | Minutes from Kick off and partner's meetings | LP | LP organizes the Kick off meeting, 1 partner meeting in Greece and prepares the minutes
| 1.4 |  | 1.4.8 |  | Closeout meeting (minutes, report & follow-up report) | LP | LP organizes the closeout meeting in Greece and prepares the minutes
| 2.1 |  | 2.1.1 |  | Communication plan | LP | LP prepares a communication plan for the dissemination of the proposed technology
| 2.3 |  | 2.3.1 |  | Publicity Material (website, TV spots, Radio spots) | LP | LP develops or upgrades a website .
| 2.4 |  | 2.4.1 |  | Newspaper entries | LP | LP publishes 4 newspaper entries to disseminate the produced results
| 2.5 |  | 2.5.1 |  | Conference presentations & proceedings | LP | LP in collaboration with P2 organizes a conference in the Achaia region
| 2.5 |  | 2.5.2 |  | Conference presentations & proceedings | LP | LP participates in a conference in Italy in Bari region organized by P6
| 2.5 |  | 2.5.3 |  | Conference presentations & proceedings | LP | LP participates in an International (WasteEng12 or VENICE 2012) and a National conference (PRE-XI or CEST2013)
| 3.1 |  | 3.1.1 |  | Physicochemical characteristics of biogas boosting wastes | LP | LP runs chemical and biological analysis of agro-waste samples provided by each partner.
| 3.2 |  | 3.2.1 |  | Supporting laboratory equipment | LP | Laboratory Equipment is commissioned by LP to support the operation of pilot plants through continuous monitoring
| 3.3 |  | 3.3.1 |  | Technical Report with lab-scale experimental results and model predictions | LP | LP runs laboratory experiments to test the efficiency of partners' agrowastes and studies the treatment of anaerobic effluent.
| 3.4 |  | 3.4.1 |  | Technical Report with results from anaerobic effluent post treatment | LP | LP runs laboratory experiments for identification of best combination of anaerobic effluent post treatment
| 4.1 |  | 4.1.1 |  | Technical specifications for pilot plant commissioning | LP | LP prepares the technical specificatios for the Italian pilot plant commissioning and supervises the proper construction of Italian pilot plant
| 4.3 |  | 4.3.1 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance | LP | LP is scientifically responsible for the operation of both Greek and Italian pilot plants for the Implementation of Greek & Italian mixtures for advanced biogas performance
| 4.4 |  | 4.4.1 |  | Technical Report with pilot scale results from anaerobic effluent post treatment | LP | LP is scientifically responsible for the implementation of best post treatment anaerobic effluent methodology on Greek & Italian pilot plants
| 4.5 |  | 4.5.1 |  | Technical Report with Greek & Italian sludges composting results | LP | LP is responsible for the composting of sludges from the operation of Greek & Italian pilot plants
| 5.1 |  | 5.1.1 |  | Technoeconomic Evaluation | LP | LP selects the best waste mixture scenarios in each partner region that maximize overall system performance based on technoeconomic evaluations of obtained results
| 5.2 |  | 5.2.1 |  | Expoitation plan | LP | LP evaluates pilot-scale results, selects the best mixtures for each partner and provides an example of exploitation plan.
| 1.1 |  | 1.1.2 |  | Project proposal | P2 | P2 provided all requested information to LP and collaborated in the preparation of the project proposal
| 1.2 |  | 1.2.2 |  | Interim and the Final report (Technical & Financial reports) | P2 | P2 provides all technical and financial information to LP for the preparation of the reports
| 1.3 |  | 1.3.2 |  | 8 Progress Reports | P2 | P2 provides all financial information to LP for the preparation of the reports
| 1.4 |  | 1.4.2 |  | Minutes from partners meeting | P2 | P2 will participate in 3 Progress/Evaluation Meetings organised by the partners
| 2.1 |  | 2.1.2 |  | Communication plan | P2 | P2 prepares a communication plan for the dissemination of the proposed technology
| 2.2 |  | 2.2.1 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) | P2 | P2 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services
| 2.3 |  | 2.3.2 |  | Website updated during the whole project | P2 | P2 contributes to the website upgrading
| 2.4 |  | 2.4.2 |  | Publicity Material (TV spots, Radio spots, newspaper entries) | P2 | P2 produces 2 TV Spots, 1 Radio Spot and prepares 4 entries in the local newspapers.
| 2.5 |  | 2.5.4 |  | Conference presentations & proceedings | P2 | P2 in collaboration with LP organizes a conference in the Achaia region and participates in a conference in Italy (Bari region) organised by P6.
| 3.1 |  | 3.1.2 |  | Technical report on estimated amounts of agro-wastes | P2 | P2 runs a survey to determine the types and amounts of agrowaste residuals in the Prefecture of Achaia
| 4.3 |  | 4.3.2 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance | P2 | P2 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production
| 4.4 |  | 4.4.2 |  | Technical Report with pilot scale results from anaerobic effluent post treatment | P2 | P2 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P2's waste mixture
| 4.5 |  | 4.5.2 |  | Technical Report with Greek & Italian sludges composting results | P2 | P2 collaborates with LP in the composting of sludges from the operation of Greek pilot plant treating P2 waste mixture
| 5.1 |  | 5.1.2 |  | Technoeconomic evaluation | P2 | P2 will conduct a study based on the indicative results from LP for the whole Achaia Prefecture.
| 5.2 |  | 5.2.2 |  | Exploitation plan | P2 | P2 will conduct a study based on the indicative results from LP for the former Prefecture of Achaia
| 1.1 |  | 1.1.3 |  | Project proposal | P3 | P3 provided all requested information to LP and collaborated in the preparation of the project proposal
| 1.2 |  | 1.2.3 |  | Interim and the Final report (Technical & Financial reports) | P3 | P3 provides all technical and financial information to LP for the preparation of the reports
| 1.3 |  | 1.3.3 |  | 8 Progress Reports | P3 | P3 provides all financial information to LP for the preparation of the reports
| 1.4 |  | 1.4.3 |  | Minutes from partners meeting | P3 | P3 will participate in 3 Progress/Evaluation Meetings organised by the partners
| 2.1 |  | 2.1.3 |  | Communication plan | P3 | P3 prepares a communication plan for the dissemination of the proposed technology
| 2.2 |  | 2.2.2 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) | P3 | P3 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services
| 2.3 |  | 2.3.3 |  | Website updated during the whole project | P3 | P3 contributes to the website upgrading
| 2.4 |  | 2.4.3 |  | Publicity Material (TV spots, Radio spots, newspaper entries) | P3 | P3 produces 1 TV Spot and prepares 4 entries in the local newspapers.
| 2.5 |  | 2.5.5 |  | Conference presentations & proceedings | P3 | P3 organizes a conference in the Aitoloakarnania region for the dissemination of its results.
| 2.5 |  | 2.5.6 |  | Conference presentations & proceedings | P3 | P3 participates in a conference in Italy (Bari region) organised by P6.
| 3.1 |  | 3.1.3 |  | Technical report on estimated amounts of agro-wastes | P3 | P3 runs a survey to determine the types and amounts of agrowaste residuals in the former Prefecture of Etoloakarnania
| 4.3 |  | 4.3.3 |  | Technical Report with Greek & Italian pilot plant operational results | P3 | P3 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production
| 4.4 |  | 4.4.3 |  | Technical Report with pilot scale results from anaerobic effluent post treatment | P3 | P3 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P3's waste mixture
| 4.5 |  | 4.5.3 |  | Technical Report with Greek & Italian sludges composting results | P3 | P3 is responsible for the composting of sludges from the operation of Greek & Italian pilot plants
| 5.1 |  | 5.1.3 |  | Technoeconomic evaluation | P3 | P3 will conduct a study based on the indicative results from LP for the former Prefecture of Etoloakarnania
| 5.2 |  | 5.2.3 |  | Exploitation plan | P3 | P3 will conduct a study based on the indicative results from LP for the former Prefecture of Etoloakarnania
| 1.1 |  | 1.1.4 |  | Project proposal | P4 | P4 provided all requested information to LP and collaborated in the preparation of the project proposal
| 1.2 |  | 1.2.4 |  | Interim and the Final report (Technical & Financial reports) | P4 | P4 provides all technical and financial information to LP for the preparation of the reports
| 1.3 |  | 1.3.4 |  | 8 Progress Reports | P4 | P4 provides all financial information to LP for the preparation of the reports
| 1.4 |  | 1.4.4 |  | Minutes from partners meeting | P4 | P4 will participate in 3 Progress/Evaluation Meetings organised by the partners
| 2.1 |  | 2.1.4 |  | Communication plan | P4 | P4 prepares a communication plan for the dissemination of the proposed technology
| 2.2 |  | 2.2.3 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) | P4 | P4 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services
| 2.3 |  | 2.3.4 |  | Website updated during the whole project | P4 | P4 contributes to the website upgrading
| 2.4 |  | 2.4.4 |  | Publicity Material (TV spots, Radio spots, newspaper entries) | P4 | P4 produces 2 TV Spots, 2 Radio Spot and prepares 8 entries in the local newspapers.
| 2.5 |  | 2.5.7 |  | Conference presentations & proceedings | P4 | P4 participates in a conference in Italy (Bari region) organised by P6
| 2.5 |  | 2.5.8 |  | Conference presentations & proceedings | P4 | P4 organizes 2 conferences in the Region of Epirus - Former Prefecture of Preveza and Arta for the dissemination of its results.
| 3.1 |  | 3.1.4 |  | Technical report on estimated amounts of agro-wastes | P4 | P4 runs a survey to determine the types and amounts of agrowaste residuals in the Region of Epirus - Former Prefecture of Preveza and Arta
| 4.3 |  | 4.3.4 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance | P4 | P4 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production
| 4.4 |  | 4.4.4 |  | Technical Report with pilot scale results from anaerobic effluent post treatment | P4 | P4 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P4's waste mixture
| 4.5 |  | 4.5.4 |  | Technical Report with Greek & Italian sludges composting results | P4 | P4 collaborates with LP in the composting of sludge from the operation of Greek pilot plant treating P4's waste mixture
| 5.1 |  | 5.1.4 |  | Technoeconomic evaluation | P4 | P4 will conduct a study based on the indicative results from LP for the Region of Epirus - Former Prefectures of Preveza and Arta.
| 5.2 |  | 5.2.4 |  | Exploitation plan | P4 | P4 will conduct a study based on the indicative results from LP for the Region of Epirus - Former Prefectures of Preveza and Arta.
| 1.1 |  | 1.1.5 |  | Project proposal | P5 | P5 provided all requested information to LP and collaborated in the preparation of the project proposal
| 1.2 |  | 1.2.5 |  | Interim and the Final report (Technical & Financial reports) | P5 | P5 provides all technical and financial information to LP for the preparation of the reports
| 1.3 |  | 1.3.5 |  | 8 Progress Reports | P5 | P5 provides all financial information to LP for the preparation of the reports
| 1.4 |  | 1.4.5 |  | Minutes from partners meeting | P5 | P5 will participate in 3 Progress/Evaluation Meetings organised by the partners
| 2.1 |  | 2.1.5 |  | Communication plan | P5 | P5 prepares a communication plan for the dissemination of the proposed technology
| 2.2 |  | 2.2.4 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) | P5 | P5 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services
| 2.3 |  | 2.3.5 |  | Website updated during the whole project | P5 | P5 contributes to the website upgrading
| 2.4 |  | 2.4.5 |  | Publicity Material (TV spots, Radio spots, newspaper entries) | P5 | P5 produces 1 TV Spots, 1 Radio Spot and prepares 4 entries in the local newspapers.
| 2.5 |  | 2.5.5 |  | Conference presentations & proceedings | P5 | P5 organizes a conference in the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki for the dissemination of its results.
| 2.5 |  | 2.5.9 |  | Conference presentations & proceedings | P5 | P5 participates in a conference in Italy (Bari) organised by P6
| 3.1 |  | 3.1.5 |  | Technical report on estimated amounts of agro-wastes | P5 | P5 runs a survey to determine the types and amounts of agrowaste residuals in the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki
| 4.3 |  | 4.3.5 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance | P5 | P5 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production
| 4.4 |  | 4.4.5 |  | Technical Report with pilot scale results from anaerobic effluent post treatment | P5 | P5 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P5's waste mixture
| 4.5 |  | 4.5.5 |  | Technical Report with Greek & Italian sludges composting results | P5 | P5 collaborates with LP in the composting of sludge from the operation of Greek pilot plant treating P5's waste mixture
| 5.1 |  | 5.1.5 |  | Technoeconomic evaluation | P5 | P5 will conduct a study based on the indicative results from LP for the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki
| 5.2 |  | 5.2.5 |  | Exploitation plan | P5 | P5 will conduct a study based on the indicative results from LP for the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki
| 1.1 |  | 1.1.6 |  | Project proposal | P6 | P6 provided all requested information to LP and collaborated in the preparation of the project proposal
| 1.2 |  | 1.2.6 |  | Interim and the Final report (Technical & Financial reports) | P6 | P6 provides all technical and financial information to LP for the preparation of the reports
| 1.3 |  | 1.3.6 |  | 8 Progress Reports | P6 | P6 provides all financial information to LP for the preparation of the reports
| 1.4 |  | 1.4.6 |  | Minutes from partners meeting | P6 | P6 will participate in 3 Progress/Evaluation Meetings organised by the partners
| 2.1 |  | 2.1.6 |  | Communication plan | P6 | P6 prepares a communication plan for the dissemination of the proposed technology
| 2.2 |  | 2.2.5 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) | P6 | P6 collaborates with P7 for the production of 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs
| 2.3 |  | 2.3.6 |  | Website updated during the whole project | P6 | P6 contributes to the website upgrading
| 2.5 |  | 2.5.10 |  | Conference presentations & proceedings | P6 | P6 organizes a conference in the Bari region for the dissemination of its results.
| 3.1 |  | 3.1.6 |  | Technical report on estimated amounts of agro-wastes | P6 | P6 runs a survey to determine the types and amounts of agrowaste residuals in the Province of Bari
| 4.1 |  | 4.1.2 |  | Italian pilot plant | P6 | Italian pilot plant is commissioned by P6 to evaluate enhanced biogas production from Italian agro-wastes
| 4.2 |  | 4.2.1 |  | Technical Report with Italian pilot plant operational results | P6 | P6 operates the Italian pilot plant. Various mixtures are tested.
| 4.3 |  | 4.3.6 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance | P6 | P6 collaborates with LP in the operation of the Italian pilot plant. Various mixtures are tested for advanced biogas production
| 4.4 |  | 4.4.6 |  | Technical Report with pilot scale results from anaerobic effluent post treatment | P6 | P6 collaborates with LP in the operation of the Italian pilot plant. Implementation of best post treatment anaerobic effluent methodology on P6's waste mixture
| 4.5 |  | 4.5.6 |  | Technical Report with Greek & Italian sludges composting results | P6 | P6 collaborates with LP in the composting of sludge from the operation of Italian pilot plant treating P6's waste mixture
| 5.1 |  | 5.1.6 |  | Technoeconomic evaluation | P6 | P6 will conduct a study based on the indicative results from LP for the whole Province of Bari.
| 5.2 |  | 5.2.6 |  | Exploitation plan | P6 | P6 will conduct a study based on the indicative results from LP for the whole Province of Bari.
| 1.1 |  | 1.1.7 |  | Project proposal | P7 | P7 provided all requested information to LP and collaborated in the preparation of the project proposal
| 1.2 |  | 1.2.7 |  | Interim and the Final report (Technical & Financial reports) | P7 | P7 provides all technical and financial information to LP for the preparation of the reports
| 1.3 |  | 1.3.7 |  | 8 Progress Reports | P7 | P7 provides all financial information to LP for the preparation of the reports
| 1.4 |  | 1.4.7 |  | Minutes from partners meeting | P7 | P7 will participate in 3 Progress/Evaluation Meetings organised by the partners
| 2.2 |  | 2.2.6 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) | P7 | P7 produces 3000 bilingual leaflets and 1000 CDs using external services
| 2.3 |  | 2.3.7 |  | Website updated during the whole project | P7 | P7 contributes to the website upgrading
| 2.4 |  | 2.4.6 |  | Publicity Material (TV spots, Radio spots, newspaper entries) | P7 | P7 produces 2 TV Spots, 1 Radio Spot and prepares 4 entries in the local newspapers.
| 2.5 |  | 2.5.11 |  | Conference presentations & proceedings | P7 | P7 organizes a conference in the Bari region for the dissemination of its results.
Location of Activities (Description of the area targeted by the project, location of partners and activities, showing the geographical scope of the longer term effects (results and impacts)
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1993
The consortium of BioGAIA includes University of Patras (located in the Region of Western Greece), 3 Regions from Greece (namely Achaia (NEA), Aitoloakarnania (ANAIT), Preveza & Arta and Kefallinia) and 2 partners from Italy, i.e. a research center (CL) and the Province of Bari (PB). The activities foreseen in the project cover therefore the whole Region of Western Greece, 2 Regions from the other eligible Regions of the Programme Area as well as the adjacent territory of Arta, where numerous dynamic industrial units exist mostly directed to the exploitation of primary production. From the Apulia Region (Italy), the Province of Bari is participating. The economy of Bari province is centred on agriculture and food processing, as revealed from a survey carried out during AGROENERGY according which, dairies, mills and other food-industries, are the most numerous with a total of 192 companies of which 40% are dairy farms, 49% olive- mills and 11% other companies (canning, wine, etc.).
In the other 2 Provinces, the percentage of food-industries is lower and is between 5 and 13% compared to the regional total. Although the participants cover partially the eligible Programm Area, the activities that will take place and moreover the anticipated results have a demonstrative character to the wider area of Greece and Italy. In fact, the wider application of the proposed technology is anticipated to contribute substantially in the solution of agroindustrial wastes management, either in solid or liquid form, that cause, at the present, an enormous environmental burden not only in the cross-border Greece-Italy are but in the whole Mediterranean region. In fact, many project deliverables will secure direct involvement of the waste output actors in both Greece & Italy, such as, farmers, cattle-breeders, cheese producers, policy makers (prefecture and region authorities), actors of the local community and potentially interested entrepreneurs (private entities, chambers, etc).
B.3 MANAGEMENT
Lead Partner and Partners Competence (Experience, Structure, Personnel, Resources, etc.)
The maximum total number of characters is 3000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 2761
The Leader Partner : University of Patras’ research activity is supported by its workforce (754 faculty members, 3260 post- and 21200 under-graduate students, postdoc researchers, etc.) supported by 481 members of permanent administrative personnel and the state of the art infrastructure (laboratories, experimental scientific instruments etc.). The University has received about 2.3 M€ for equipment and 28 M€ for R+D, just for 2008, from the EU while it also receives funding from the State and the private sector. The scientific representative of UPatras, Assist. Prof. Michael Kornaros, has participated in 4 INTERREG IIIA projects (2006-2009), i.e. AGROENERGY, GOW, POPULAR, BIOSIS and in more than 50 national and EU-funded projects in the last 15 years. The Development Agency of Aitoloakarnania Prefecture (ANAIT) S.A. is implementing a series of EU and National Programs with the effort of 25 members of its staff. ANAIT has obtained certification ISO 9001 and has constructed
its new business plan. Development Enterprise of Achaia Prefecture (NEA) has implemented and maintains a "Quality Management System" (by DQS GmbH) for the activities: "Technical and Financial Management of public interest projects", according to the standard DIN EN ISO 9001:2000. NEA has also been certified by the Management Authority of The Region of Western Greece for the materialization of sentences and supplies (type B). Particular experience in INTERREG projects : AGROENERGY, POPULAR, SEMINET, IT-PORT, ARCHEOTOUR, LOC-PRO, DEBATE, MILUNET. The Region of Epirus - Former Prefectures of Preveza & Arta is responsible for the administration of national funds transferred by central government and takes over EU Projects that support regional growth in many sectors (e.g. trade, agriculture, health, etc.).
The Former Prefectures of Preveza & Arta have acquired significant experience in the management of EU Projects by participating in projects either as Lead Partner (INTERREG IIIA Greece-Italy) or as partner. Region of Ionian Islands' Administration personnel are highly educated, with long-experience in Structural Funds and increasingly participation in EU Programs. Centro Laser (CL) is a research and technology transfer centre that has been operating since 1979 in collaboration with universities, research centres, public administration and private companies. The CL staff consists of physicists, engineers computers engineers, chemists and technicians of different training. The Province of Bari is among the largest and most populated in Italy and is administratively divided into 41 Municipalities. The Province of Bari has participated in many national and EU funded programmes including INTERREG IIIA (participated also in AGROENERGY among others).
Project Management & Coordination (structures, decision making procedures, internalcommunication, etc)
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1988
The surveillance of projects’ activities and operations is achieved through the constitution of a Technical Committee with the participation of at least one managerially experienced member, of each beneficiary. The Technical Committee will be in charge of the coordination of operations, for the management and the communication, among the partners, as well as for the contractual management of the Project on daily basis. In order to ensure the efficient implementation of these tasks, a Scientific Coordinator will be appointed. The meetings of the Technical Committee will take place simultaneously with the meetings of the Coordinating Team, as the Technical Committee is part of the Coordinating Team. Both Scientific Coordinator and Financial Manager have a frequent and direct communication with all the partners’ contact persons, as well as with the Project Coordinator who is responsible for the communication with the responsible department of the MA/JTS. While the Scientific Coordinator
mainly deals with the operational reports and synthesizes the overall picture of the operation, the Financial Manager receives the financial reports and controls the eligibility of the costs and the documentation. Together they construct the Progress Reports as well as the Interim and Final Report for the whole partnership. Afterwards the reports are notified to the Project Coordinator for final evaluation and control. The Project Coordinator is responsible for the organisation of the entire project work and the mobilization of the partners, with a particular focus on the issues and up-to-date topics of financial and contractual management, administration and coordination, including the self-evaluation. The meetings provide added value to the transparency and shared ownership of the project. During the sessions the members focus on the administrative and technical protocol, the time plan of the project, the communication among partners and the quality of the working methods.
B.4 INFORMATION AND PUBLICITY
Information and Publicity measures- external communication of project outputs, results etc.
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1991
One of the first actions that will be implemented in the BioGAIA project is the common development from the 1st month of the project’s life a Plan for Communication for each one of the partners. This plan will describe in detail the information and publicity measures that will be taken during the project’s life. Since the information material is the backbone of every dissemination and publicity programme, specific sets of such material will be developed from each partner. This includes e.g. bilingual leaflets (3000), posters (1000), CDs (1000) and 4 biannual newsletters. The Information material will be supplemented by publicity material which will include: a website, 8 TV-spots (6-months presentation in local TV-station), 5 Radio spots (6-months presentation in local Radio-station) and 24 entries in local newspapers. A number of complementary strategies will be adopted within the life-time of the BioGAIA project. University of Patras in order to secure the overall project
dissemination will promote the usual form of academic research dissemination, i.e. publications of the scientific results in international and national scientific and technical journals, presentation in national and international conferences, participation in patent applications, through graduate training programs, and PhD programs. A number of the papers presented at conferences will also be published in conference proceedings. In fact, University of Patras envisages participating at least in 2 conferences, 1 international and one national. Moreover, local conferences (100 participants) will also be organized from each partner separately both in Greece and Italy in the aim to disseminate as efficiently as possible the program’s results directly to the waste output actors, such as, farmers, cattle-breeders, oil and cheese producers, policy makers (prefecture and region authorities), actors of the local community and potentially interested entrepreneurs (private entities, chambers, etc)
B.5 MATURITY OF THE PROJECT
Preparatory activities, administrative activities undetaken etc.
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1994
In the framework of implementing two previous relevant INTERREG IIIA projects, i.e POPULAR abd AGROENERGY, local workshops to the interested stakeholders (olive-mill oil producers, representatives from the Prefectures, entrepreneurs, etc) presenting these projects' results revealed their vivid interest in finding a solution to the problem of their wastes treatment. The environmental problem that has been identified by all participants is enormous in both Greek and Italian territories. However the cost of the proposed solution hinders the realization of these plants. Although the capital cost required for the construction of such central AD plants is quite high, for the standards of small to medium agro-food enterprises, the proposed anaerobic co-digestion plants are sustainable having a pay-back time of about 4,5 years (without external co-funding). Therefore, the only viable solution for their problems is to make these plants even more attractive, from the sustainability point of view
in order to convert them from waste treatment plants into biogas production plants attractive for green entrepreneurs. So consultations with all relevant stakeholders have proven that the only solution to realize this technology into actual full-scale plants is to demonstrate the technology and its viability as widely as possible. To this end, all participating Prefectures in the AGROENERGY project have verified in their Prefectural Boards their vivid willingness to continue their efforts to this common target and therefore participate in the proposed project of BioGAIA. The advantages of the proposed technology are so obvious and the proposed solution seems as the only viable one for this type of wastes that even more Prefectures than those participated in AGROENERGY have expressed their willingness to participate in BioGAIA, namely the Former Prefectures of Aitoloakarnania and Arta, because of the size of the environmental problem they are currently facing and has to be solved.
B.6 SUSTAINABILITY OF RESULTS
Sustainability of results and follow-up actions
The maximum total number of characters is 1000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 2096
Construction and operation of pilot plants aims to demonstrate an innovative methodology for the exploitation of agro-wastes producing renewable energy and high quality compost. It is critical for both the LP and more for the partners to maintain the pilot plants under operation after the end of the project’s lifetime in order to attract potential investors that could take advantage of the specific technology. Specific follow-up activities that will be undertaken in the Region of Western Greece and the Province of Bari include: • Before the start of each school year, an announcement will be sent to all schools of Achaia and in Bari in order to invite teachers and students to visit the pilot plants. • The pilot plants will be included as place of interest at the local Investors Reception Point (supervised by the Former Achaia Prefecture and the Province of Bari). • Maintenance of the web site will be undertaken by LP that they will operate for at least 5 years after the project’s end.
The purpose of constructing pilot plants is clearly for demonstrating an innovative methodology for the waste management treatment producing renewable energy and high quality compost. It is critical for both the University of Patras and more for the partners where the pilots will remain after the project ends (Prefecture of Achaia and Centro Laser), to maintain the pilot plants under operation after the end of the project’s lifetime. The reason is that the demonstrating activities of the specific BioGAIA solution will continue even after the end of the project, in order to attract potential investors that could take advantage of the specific technology and the project results in order to invest in industrial scale plants. The Prefecture of Achaia and Centro Laser will undertake all the necessary operational costs for the proper operation of the pilot plants from their annual budgets. Furthermore, the University of Patras will provide the appropriate scientific personnel in order to monitor and to certify the pilot plant’s proper operation after the end of the project’s life time.
B.7 CROSS-BORDER COOPERATION & ADDED VALUE
Intensity of Cross-Border Cooperation
Please describe in which ways shall the partners co-operate (min two of the following four: joint development, joint implementation, joint staffing, joint financing) as well as the added value that will be accomplished through this co-operation
|  |  | x | Joint Development
|  |  | x | Joint implementation
|  |  | x | Joint staffing
|  |  | x | Join Financing
Cross-Border cooperation and capitalization
| The maximum total number of characters is 1000 | [8 empty] | Number of characters | 981
The project BioGAIA emerged from the collaboration between the University of Patras, Former Prefectures of Achaia, Kefallinia, Leykada and Preveza from Greece, Province of Bari and Centro Ricerche of Bonomo from Italy as part of the European Community Initiative INTERREG IIIA Greece-Italy 2000-2006, project “AGROENERGY” (Code No I3101004), in which we investigated the fermentative methane production from agroindustrial wastewaters, namely olive mill wastewaters, cheese whey wastewater and liquid cow manure. The lab-results obtained from the AGROENERGY project were pretty encouraging since they proved that continuous methane production from these kinds of wastewaters is feasible and stable. A pilot plant was constructed by the Prefecture of Achaia in the Industrial Zone of Patras (Greece) to be used for process scale-up and pilot testing of the available agrowastes within the regions involved but practically operated only for a while due to lack of project's lifetime.
B.8 COMPATIBILITY WITH EU AND NATIONAL POLICIES
Consistency of the project with EU horizontal policies
Equal opportunities
Please state if the project will :
have its main focus on equal opportunities
|  |  | x | be positive in terms of equal opportunities
be neutral in terms of equal opportunities
Sustainable Development
Please state if the project will :
|  |  | x | it mainly focuses on Sustainable Development
be positive in terms of Sustainable Development
be neutral in terms of Sustainable Development
Environmental Impact (Please fill in the environmental indicators in Section F)
Please state if the project will :
|  |  | x | it mainly focuses on Environment
be positive in terms of Enviornment
be neutral in terms of Environment
Open Market
Please state if the project will :
it mainly focuses on fair competition / open market
|  |  | x | be positive in terms of fair competition / open market
be neutral in terms of fair competition / open market
Other EU, National, Regional and Local Policies (please specify)
The maximum total number of characters is 2000
| (please do not exceed 1000 characters in each box) | [8 empty] | Number of characters | 1974
The BioGAIA project is in line with the national priority for waste and natural resources and the specific national target for maximising the recovery of energy and materials from wastes through the development of methods of wastes exploitation. More specifically the promotion of electricity from renewable energy sources (RES) is a high European Union (EU) and national priority for combating climate change and several other reasons, including the security and diversification of energy supply, environmental protection and social and economic cohesion (e.g. Directive 2001/77/EC). Furthermore, a specific national target also addressed by the BioGAIA project is the Reuse of treated wastewaters. Moreover, promotion of decentralised anaerobic digesters (biogas plants) applied in conjunction with CHP technologies is in agreement with EU policy, as expressed in European Commission’s “Green Paper”:  Decentralised Anaerobic Digesters offer the advantage of locally produced fuels exploitation,
including poor quality fuels, biomass and wastes. According to the “Green Paper”, efforts should be made to promote new and renewable energy sources (such as hydrogen and cogeneration) in our economies. The European Union has set itself an ambitious target in this respect: 12% of energy consumption in 2010 should come from Renewables.  Promotion of Anaerobic Digesters for agrowastes is in accordance to EU policy for energy development, since it offers the means to improve energy efficiency, reduce energy intensity and vastly increase the share of clean, durable and renewable energy use. It also has a potential to influence global patterns of energy use and production, as advanced European technologies can provide developing countries with more sustainable and less damaging means towards economic growth.  Implementations of such technologies contribute to reduction of gaseous emissions in power generation and compliance with the Kyoto protocol restrictions.
Formulas:
Start = MIN([Start, row below]:R195)
End = MAX([End, row below]:T195)

## Partnership
SECTION C - PARTNERSHIP
Lead Partner (P1) Details
Name of institution in English | University of Patras - ELKE
Name of institution in original language | Πανεπιστήμιο Πατρών - ΕΛΚΕ
Distinctive Title | UPAT
Legal Status | governed by public law
Legal Representative | Prof. Dimitrios L. Kalpaxis
Position of the legal representative in the organisation | Vice-Rector of Strategic Research Planning and Development
Contact Person for the project | Assist.Prof. Michael Kornaros
Project Manager | Assist.Prof. Michael Kornaros
Financial Manager | George Vakakis
Address | 1 Karatheodori st., University Campus - Rio, 26500, Patras
Country | Greece
NUTS III code | Prefecture of Achaia
Telephone | +30 2610 997418
e-mail | kornaros@chemeng.upatras.gr
fax | +30 2610 969516
website | www.upatras.gr
VAT status (eligible or not) | Eligible
Tax Office | Α΄ Patras’ Tax Office
Tax Number | EL 998219694
Budget of Lead Partner
Total Budget | 410000
ERDF | 307500
National Contribution | 102500
Bank Details of Lead Partner
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 2 (P2) Details
Name of institution in English | Development Enterprise of Achaia
Name of institution in original language | Νομαρχιακή Επιχείρηση Ανάπτυξης Αχαΐας
Distinctive Title | NEA
Legal Status | governed by public law
Legal Representative | George Athanasopoulos
Position of the legal representative in the organisation | President of Board of Directors
Contact Person for the project | Kostas Giotopoulos
Address | 8, D. Ipsilantou & Mezonos Str., GR 26222, Patras
Country | Greece
NUTS III code | Prefecture of Achaia
Telephone | +30 2610318224
e-mail | nea@nea.gr
fax | +30 2610317877
website | www.nea.gr
VAT status (eligible or not) | not-eligible
Tax Office | B' Patras' Tax Office
Tax Number | EL 090268479
Budget of P2
Total Budget | 135000
ERDF | 101250
National Contribution | 33750
Bank Details of P2
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 3 (P3) Details
Name of institution in English | Development Agency of Etoloakarnania Prefecture (ANAIT) S.A.
Name of institution in original language | Αναπτυξιακή Αιτωλοακαρνανίας (ΑΝΑΙΤ) Α.Ε. ΟΤΑ
Distinctive Title | ΑΝΑΙΤ S.A.
Legal Status | governed by public law
Legal Representative | Konstantinos Karanikas
Position of the legal representative in the organisation | President of Board of Directors
Contact Person for the project | Spyros Koufos
Address | 41 Kyprou St, 30200 Messolonghi
Country | Greece
NUTS III code | Prefecture of Aitoloakarnania
Telephone | +30 2631055140
e-mail | anait@otenet.gr
fax | +30 2631026103
website | www.anait.gr
VAT status (eligible or not) | not-eligible
Tax Office | Messolonghi
Tax Number | EL 094193837
Budget of P3
Total Budget | 115000
ERDF | 86250
National Contribution | 28750
Bank Details of P3
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 4 (P4) Details
Name of institution in English | Region of Epirus - Former Prefectures of Preveza and Arta
Name of institution in original language | Περιφέρεια Ηπείρου
Distinctive Title
Legal Status | Public
Legal Representative | Alexandros Kachrimanis
Position of the legal representative in the organisation | Regional Administrator
Contact Person for the project | Frixos Nassis (Preveza)/ Vasiliki Zisi (Arta)
Address | 8 Spiliadou, 48100 Preveza / Ethnikis Antistasis Square, Arta
Country | Greece
NUTS III code | Prefecture of Ioannina
Telephone | +30 2682360280 / 2681361017
e-mail | kitsantas@preveza.gr / v.zisi@php.gov.gr
fax | +30 2682022476 / +30 2681075855
website | www.preveza.gr / www.nomarxia-artas.gr
VAT status (eligible or not) | Eligible
Tax Office | A' Tax Office of Ioannina
Tax Number | EL 997908822
Budget of P4
Total Budget | 186000
ERDF | 139500
National Contribution | 46500
Bank Details of P4
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 5 (P5) Details
Name of institution in English | Region of Ionian Islands - Former Prefecture of Kefallinia & Ithaki
Name of institution in original language | Περιφέρεια Ιονίων Νήσων
Distinctive Title
Legal Status | public
Legal Representative | Spiridon Spirou
Position of the legal representative in the organisation | Regional Administrator
Contact Person for the project | Alexandra Ladou
Address | Samara 13 49100-Corfu
Country | Greece
NUTS III code | Prefecture of Kerkyra/Corfu
Telephone | +30 26713-60516
e-mail | alexladou@yahoo.gr
fax | +30 26710-29075
website | www.kefalonia.eu
VAT status (eligible or not) | Eligible
Tax Office | A' Tax Office of Kerkyra
Tax Number | EL 997913715
Budget of P5
Total Budget | 115000
ERDF | 86250
National Contribution | 28750
Bank Details of P5
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 6 (P6) Details
Name of institution in English | Laser Center
Name of institution in original language | Centro Laser S.c.a.r.l.
Distinctive Title | CL
Legal Status | governed by public law
Legal Representative | Prof. Francesco Fracassi
Position of the legal representative in the organisation | President
Contact Person for the project | Patrizia Boffi
Address | Str. Prov. Per Casamassima km 3 - 70100 Valenzano (BA)
Country | Italy
NUTS III code | Province of Bari
Telephone | 0039 080 4674314
e-mail | Patrizia.boffi@centrolaser.it
fax | 0039 080 4674457
website | www.centrolaser.it
VAT status (eligible or not) | not-eligible
Tax Office | Agenzia delle Entrate di Bari
Tax Number | IT 01167400728
Budget of P6
Total Budget | 420000
ERDF | 315000
National Contribution | 105000
Bank Details of P6
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 7 (P7) Details
Name of institution in English | Province of Bari
Name of institution in original language | Provincia di Bari
Distinctive Title
Legal Status | public
Legal Representative | Prof. Francesco Schittulli
Position of the legal representative in the organisation | President
Contact Person for the project | Dr. Francesco Degiorgio
Address | via Spalato n. 19 - Bari
Country | Italy
NUTS III code | Province of Bari
Telephone | 00390805412644
e-mail | f.degiorgio@provincia.ba.it
fax | 00390805580161
website | www.provincia.ba.it
VAT status (eligible or not) | eligible
Tax Office | MINISTERY OF ECONOMY - INCOME AGENCY BA/2
Tax Number | 80000110728
Budget of P7
Total Budget | 25000
ERDF | 18750
National Contribution | 6250
Bank Details of P7
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 8 (P8) Details
Name of institution in English
Name of institution in original language
Distinctive Title
Legal Status
Legal Representative
Position of the legal representative in the organisation
Contact Person for the project
Address
Country
NUTS III code
Telephone
e-mail
fax
website
VAT status (eligible or not)
Tax Office
Tax Number
Budget of P8
Total Budget | 0
ERDF | 0
National Contribution | 0
Bank Details of P8
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 9 (P9) Details
Name of institution in English
Name of institution in original language
Distinctive Title
Legal Status
Legal Representative
Position of the legal representative in the organisation
Contact Person for the project
Address
Country
NUTS III code
Telephone
e-mail
fax
website
VAT status (eligible or not)
Tax Office
Tax Number
Budget of P9
Total Budget | 0
ERDF | 0
National Contribution | 0
Bank Details of P9
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account
Partner 10 (P10) Details
Name of institution in English
Name of institution in original language
Distinctive Title
Legal Status
Legal Representative
Position of the legal representative in the organisation
Contact Person for the project
Address
Country
NUTS III code
Telephone
e-mail
fax
website
VAT status (eligible or not)
Tax Office
Tax Number
Budget of P10
Total Budget | 0
ERDF | 0
National Contribution | 0
Bank Details of P10
(to be completed upon approval)
Bank Name
Address
Postal Code
Town
Country
IBAN
SWIFT code
Holder of the account

## Budget
SECTION D - BUDGET
Project Budget
| ERDF |  |  |  | 1054500
| National co-financing |  |  |  | 351500
| Total Budget |  |  |  | 1406000
Total Costs per Action / Budget Line
|  |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 61600 |  | 44373 | 39155 | 41700 |  | 7695 | 0 | 0 |  | 194523
| Action 1.1 |  | 8700 |  | 4 | 0 | 0 |  | 0 | 0 | 0 |  | 8704
| Action 1.2 |  | 21500 |  | 1018 | 0 | 9900 |  | 7695 | 0 | 0 |  | 40113
| Action 1.3 |  | 22600 |  | 42265 | 0 | 28800 |  | 0 | 0 | 0 |  | 93665
| Action 1.4 |  | 8800 |  | 1086 | 39155 | 3000 |  | 0 | 0 | 0 |  | 52041
| Action 1.5 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| WP 2 |  | 51100 |  | 8997 | 21495 | 135825 |  | 0 | 0 | 2400 |  | 219817
| Action 2.1 |  | 14900 |  | 1000 | 0 | 5900 |  | 0 | 0 | 0 |  | 21800
| Action 2.2 |  | 5300 |  | 1087 | 150 | 41500 |  | 0 | 0 | 0 |  | 48037
| Action 2.3 |  | 11200 |  | 1012 | 0 | 10500 |  | 0 | 0 | 0 |  | 22712
| Action 2.4 |  | 600 |  | 213 | 50 | 50925 |  | 0 | 0 | 0 |  | 51788
| Action 2.5 |  | 19100 |  | 5685 | 21295 | 27000 |  | 0 | 0 | 2400 |  | 75480
| WP 3 | Title | 83300 |  | 2000 | 1250 | 32000 |  | 185000 | 0 | 29310 |  | 332860
| Action 3.1 |  | 42200 |  | 2000 | 1250 | 32000 |  | 0 | 0 | 13810 |  | 91260
| Action 3.2 |  | 2500 |  | 0 | 0 | 0 |  | 185000 | 0 | 0 |  | 187500
| Action 3.3 |  | 26000 |  | 0 | 0 | 0 |  | 0 | 0 | 8000 |  | 34000
| Action 3.4 |  | 12600 |  | 0 | 0 | 0 |  | 0 | 0 | 7500 |  | 20100
| Action 3.5 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| WP 4 | Title | 151250 |  | 5000 | 12020 | 61000 |  | 200000 | 0 | 56030 |  | 485300
| Action 4.1 |  | 12500 |  | 1000 | 5770 | 0 |  | 200000 | 0 | 10000 |  | 229270
| Action 4.2 |  | 10000 |  | 1000 | 2750 | 10000 |  | 0 | 0 | 5000 |  | 28750
| Action 4.3 |  | 58350 |  | 1000 | 0 | 14000 |  | 0 | 0 | 20965 |  | 94315
| Action 4.4 |  | 25550 |  | 1000 | 2500 | 14000 |  | 0 | 0 | 10065 |  | 53115
| Action 4.5 |  | 44850 |  | 1000 | 1000 | 23000 |  | 0 | 0 | 10000 |  | 79850
| WP 5 | Title | 99100 |  | 4000 | 0 | 70400 |  | 0 | 0 | 0 |  | 173500
| Action 5.1 |  | 36000 |  | 2000 | 0 | 3000 |  | 0 | 0 | 0 |  | 41000
| Action 5.2 |  | 63100 |  | 2000 | 0 | 67400 |  | 0 | 0 | 0 |  | 132500
| Action 5.3 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 5.4 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 5.5 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.3 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.4 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.5 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| TOTALS |  | 446350 |  | 64370 | 73920 | 340925 |  | 392695 | 0 | 87740 |  | 1406000
Costs per Partner / Action / Budget Line
| Lead Partner (LP) |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 30800 |  | 20500 | 4905 | 7000 |  | 0 | 0 | 0 |  | 63205
| Action 1.1 |  | 3000 | [9 empty] | 3000
| Action 1.2 |  | 10000 | [9 empty] | 10000
| Action 1.3 |  | 14400 |  | 20500 |  | 5000 | [5 empty] | 39900
| Action 1.4 |  | 3400 |  |  | 4905 | 2000 | [5 empty] | 10305
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 11200 |  | 0 | 8015 | 3500 |  | 0 | 0 | 2400 |  | 25115
| Action 2.1 |  | 1400 | [9 empty] | 1400
| Action 2.2 | [11 empty] | 0
| Action 2.3 |  | 5600 | [9 empty] | 5600
| Action 2.4 | [5 empty] | 2000 | [5 empty] | 2000
| Action 2.5 |  | 4200 |  |  | 8015 | 1500 |  |  |  | 2400 |  | 16115
| WP 3 | Title | 42800 |  | 0 | 0 | 0 |  | 185000 | 0 | 22710 |  | 250510
| Action 3.1 |  | 1700 | [7 empty] | 7210 |  | 8910
| Action 3.2 |  | 2500 | [5 empty] | 185000 |  |  |  | 187500
| Action 3.3 |  | 26000 | [7 empty] | 8000 |  | 34000
| Action 3.4 |  | 12600 | [7 empty] | 7500 |  | 20100
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 42900 |  | 0 | 3270 | 0 |  | 0 | 0 | 15000 |  | 61170
| Action 4.1 |  | 2500 |  |  | 3270 | [6 empty] | 5770
| Action 4.2 | [11 empty] | 0
| Action 4.3 |  | 24350 | [7 empty] | 5000 |  | 29350
| Action 4.4 |  | 3400 | [7 empty] | 5000 |  | 8400
| Action 4.5 |  | 12650 | [7 empty] | 5000 |  | 17650
| WP 5 | Title | 10000 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10000
| Action 5.1 |  | 5000 | [9 empty] | 5000
| Action 5.2 |  | 5000 | [9 empty] | 5000
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 137700 |  | 20500 | 16190 | 10500 |  | 185000 | 0 | 40110 |  | 410000
| P2 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 7500 |  | 6750 | 4830 | 6000 |  | 2000 | 0 | 0 |  | 27080
| Action 1.1 | [11 empty] | 0
| Action 1.2 |  | 5000 | [5 empty] | 2000 |  |  |  | 7000
| Action 1.3 |  | 2500 |  | 6750 |  | 5000 | [5 empty] | 14250
| Action 1.4 |  |  |  |  | 4830 | 1000 | [5 empty] | 5830
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 12500 |  | 0 | 3220 | 21485 |  | 0 | 0 | 0 |  | 37205
| Action 2.1 |  | 3000 | [9 empty] | 3000
| Action 2.2 |  | 2500 |  |  |  | 5000 | [5 empty] | 7500
| Action 2.3 |  | 2000 |  |  |  | 2500 | [5 empty] | 4500
| Action 2.4 | [5 empty] | 7985 | [5 empty] | 7985
| Action 2.5 |  | 5000 |  |  | 3220 | 6000 | [5 empty] | 14220
| WP 3 | Title | 10000 |  | 0 | 0 | 0 |  | 0 | 0 | 1200 |  | 11200
| Action 3.1 |  | 10000 | [7 empty] | 1200 |  | 11200
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 24950 |  | 0 | 0 | 0 |  | 0 | 0 | 7065 |  | 32015
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 |  | 10600 | [7 empty] | 5000 |  | 15600
| Action 4.4 |  | 3750 | [7 empty] | 2065 |  | 5815
| Action 4.5 |  | 10600 | [9 empty] | 10600
| WP 5 | Title | 27500 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 27500
| Action 5.1 |  | 2500 | [9 empty] | 2500
| Action 5.2 |  | 25000 | [9 empty] | 25000
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 82450 |  | 6750 | 8050 | 27485 |  | 2000 | 0 | 8265 |  | 135000
| P3 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 8000 |  | 0 | 4830 | 2000 |  | 2000 | 0 | 0 |  | 16830
| Action 1.1 |  | 2500 | [9 empty] | 2500
| Action 1.2 |  | 2500 | [5 empty] | 2000 |  |  |  | 4500
| Action 1.3 |  | 2000 |  |  |  | 2000 | [5 empty] | 4000
| Action 1.4 |  | 1000 |  |  | 4830 | [6 empty] | 5830
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 10000 |  | 5625 | 3220 | 16970 |  | 0 | 0 | 0 |  | 35815
| Action 2.1 |  | 5000 | [9 empty] | 5000
| Action 2.2 | [5 empty] | 6500 | [5 empty] | 6500
| Action 2.3 | [5 empty] | 2000 | [5 empty] | 2000
| Action 2.4 | [5 empty] | 5970 | [5 empty] | 5970
| Action 2.5 |  | 5000 |  | 5625 | 3220 | 2500 | [5 empty] | 16345
| WP 3 | Title | 8500 |  | 0 | 0 | 0 |  | 0 | 0 | 1800 |  | 10300
| Action 3.1 |  | 8500 | [7 empty] | 1800 |  | 10300
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 17900 |  | 0 | 0 | 0 |  | 0 | 0 | 4655 |  | 22555
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 |  | 5700 | [7 empty] | 3655 |  | 9355
| Action 4.4 |  | 6900 | [7 empty] | 1000 |  | 7900
| Action 4.5 |  | 5300 | [9 empty] | 5300
| WP 5 | Title | 13100 |  | 0 | 0 | 16400 |  | 0 | 0 | 0 |  | 29500
| Action 5.1 |  | 5000 |  |  |  | 3000 | [5 empty] | 8000
| Action 5.2 |  | 8100 |  |  |  | 13400 | [5 empty] | 21500
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 57500 |  | 5625 | 8050 | 35370 |  | 2000 | 0 | 6455 |  | 115000
| P4 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 4000 |  | 8370 | 10860 | 14000 |  | 1695 | 0 | 0 |  | 38925
| Action 1.1 | [11 empty] | 0
| Action 1.2 |  | 1500 |  |  |  | 9500 |  | 1695 |  |  |  | 12695
| Action 1.3 |  | 1500 |  | 8370 |  | 4500 | [5 empty] | 14370
| Action 1.4 |  | 1000 |  |  | 10860 | [6 empty] | 11860
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 2000 |  | 0 | 3620 | 40000 |  | 0 | 0 | 0 |  | 45620
| Action 2.1 |  | 1000 |  |  |  | 3000 | [5 empty] | 4000
| Action 2.2 | [5 empty] | 11000 | [5 empty] | 11000
| Action 2.3 | [5 empty] | 4000 | [5 empty] | 4000
| Action 2.4 | [5 empty] | 14000 | [5 empty] | 14000
| Action 2.5 |  | 1000 |  |  | 3620 | 8000 | [5 empty] | 12620
| WP 3 | Title | 2000 |  | 0 | 0 | 12000 |  | 0 | 0 | 1800 |  | 15800
| Action 3.1 |  | 2000 |  |  |  | 12000 |  |  |  | 1800 |  | 15800
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 5000 |  | 0 | 0 | 41000 |  | 0 | 0 | 4655 |  | 50655
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 |  | 2000 |  |  |  | 14000 |  |  |  | 3655 |  | 19655
| Action 4.4 |  | 1000 |  |  |  | 14000 |  |  |  | 1000 |  | 16000
| Action 4.5 |  | 2000 |  |  |  | 13000 | [5 empty] | 15000
| WP 5 | Title | 1000 |  | 0 | 0 | 34000 |  | 0 | 0 | 0 |  | 35000
| Action 5.1 |  | 1000 | [9 empty] | 1000
| Action 5.2 | [5 empty] | 34000 | [5 empty] | 34000
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 14000 |  | 8370 | 14480 | 141000 |  | 1695 | 0 | 6455 |  | 186000
| P5 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 0 |  | 5625 | 4830 | 11500 |  | 2000 | 0 | 0 |  | 23955
| Action 1.1 | [11 empty] | 0
| Action 1.2 | [7 empty] | 2000 |  |  |  | 2000
| Action 1.3 |  |  |  | 5625 |  | 11500 | [5 empty] | 17125
| Action 1.4 |  |  |  |  | 4830 | [6 empty] | 4830
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 5000 |  | 0 | 3220 | 34370 |  | 0 | 0 | 0 |  | 42590
| Action 2.1 |  | 2500 |  |  |  | 2900 | [5 empty] | 5400
| Action 2.2 | [5 empty] | 16000 | [5 empty] | 16000
| Action 2.3 | [5 empty] | 2000 | [5 empty] | 2000
| Action 2.4 | [5 empty] | 10970 | [5 empty] | 10970
| Action 2.5 |  | 2500 |  |  | 3220 | 2500 | [5 empty] | 8220
| WP 3 | Title | 5000 |  | 0 | 0 | 0 |  | 0 | 0 | 1800 |  | 6800
| Action 3.1 |  | 5000 | [7 empty] | 1800 |  | 6800
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 14500 |  | 0 | 0 | 0 |  | 0 | 0 | 4655 |  | 19155
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 |  | 6700 | [7 empty] | 3655 |  | 10355
| Action 4.4 |  | 2500 | [7 empty] | 1000 |  | 3500
| Action 4.5 |  | 5300 | [9 empty] | 5300
| WP 5 | Title | 2500 |  | 0 | 0 | 20000 |  | 0 | 0 | 0 |  | 22500
| Action 5.1 |  | 2500 | [9 empty] | 2500
| Action 5.2 | [5 empty] | 20000 | [5 empty] | 20000
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 27000 |  | 5625 | 8050 | 65870 |  | 2000 | 0 | 6455 |  | 115000
| P6 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 10000 |  | 3000 | 5000 | 0 |  | 0 | 0 | 0 |  | 18000
| Action 1.1 |  | 3000 | [9 empty] | 3000
| Action 1.2 |  | 2000 |  | 1000 | [7 empty] | 3000
| Action 1.3 |  | 2000 |  | 1000 | [7 empty] | 3000
| Action 1.4 |  | 3000 |  | 1000 | 5000 | [6 empty] | 9000
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 7000 |  | 3000 | 0 | 5000 |  | 0 | 0 | 0 |  | 15000
| Action 2.1 |  | 2000 |  | 1000 | [7 empty] | 3000
| Action 2.2 |  | 2000 |  | 1000 | [7 empty] | 3000
| Action 2.3 |  | 3000 |  | 1000 | [7 empty] | 4000
| Action 2.4 | [11 empty] | 0
| Action 2.5 | [5 empty] | 5000 | [5 empty] | 5000
| WP 3 | Title | 15000 |  | 2000 | 1250 | 20000 |  | 0 | 0 | 0 |  | 38250
| Action 3.1 |  | 15000 |  | 2000 | 1250 | 20000 | [5 empty] | 38250
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 46000 |  | 5000 | 8750 | 20000 |  | 200000 | 0 | 20000 |  | 299750
| Action 4.1 |  | 10000 |  | 1000 | 2500 |  |  | 200000 |  | 10000 |  | 223500
| Action 4.2 |  | 10000 |  | 1000 | 2750 | 10000 |  |  |  | 5000 |  | 28750
| Action 4.3 |  | 9000 |  | 1000 | [7 empty] | 10000
| Action 4.4 |  | 8000 |  | 1000 | 2500 | [6 empty] | 11500
| Action 4.5 |  | 9000 |  | 1000 | 1000 | 10000 |  |  |  | 5000 |  | 26000
| WP 5 | Title | 45000 |  | 4000 | 0 | 0 |  | 0 | 0 | 0 |  | 49000
| Action 5.1 |  | 20000 |  | 2000 | [7 empty] | 22000
| Action 5.2 |  | 25000 |  | 2000 | [7 empty] | 27000
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 123000 |  | 17000 | 15000 | 45000 |  | 200000 | 0 | 20000 |  | 420000
| P7 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 1300 |  | 128 | 3900 | 1200 |  | 0 | 0 | 0 |  | 6528
| Action 1.1 |  | 200 |  | 4 | [7 empty] | 204
| Action 1.2 |  | 500 |  | 18 |  | 400 | [5 empty] | 918
| Action 1.3 |  | 200 |  | 20 |  | 800 | [5 empty] | 1020
| Action 1.4 |  | 400 |  | 86 | 3900 | [6 empty] | 4386
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 3400 |  | 372 | 200 | 14500 |  | 0 | 0 | 0 |  | 18472
| Action 2.1 | [11 empty] | 0
| Action 2.2 |  | 800 |  | 87 | 150 | 3000 | [5 empty] | 4037
| Action 2.3 |  | 600 |  | 12 | [7 empty] | 612
| Action 2.4 |  | 600 |  | 213 | 50 | 10000 | [5 empty] | 10863
| Action 2.5 |  | 1400 |  | 60 |  | 1500 | [5 empty] | 2960
| WP 3 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 3.1 | [11 empty] | 0
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 | [11 empty] | 0
| Action 4.4 | [11 empty] | 0
| Action 4.5 | [11 empty] | 0
| WP 5 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 5.1 | [11 empty] | 0
| Action 5.2 | [11 empty] | 0
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 4700 |  | 500 | 4100 | 15700 |  | 0 | 0 | 0 |  | 25000
| P8 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 1.1 | [11 empty] | 0
| Action 1.2 | [11 empty] | 0
| Action 1.3 | [11 empty] | 0
| Action 1.4 | [11 empty] | 0
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 2.1 | [11 empty] | 0
| Action 2.2 | [11 empty] | 0
| Action 2.3 | [11 empty] | 0
| Action 2.4 | [11 empty] | 0
| Action 2.5 | [11 empty] | 0
| WP 3 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 3.1 | [11 empty] | 0
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 | [11 empty] | 0
| Action 4.4 | [11 empty] | 0
| Action 4.5 | [11 empty] | 0
| WP 5 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 5.1 | [11 empty] | 0
| Action 5.2 | [11 empty] | 0
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| P9 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 1.1 | [11 empty] | 0
| Action 1.2 | [11 empty] | 0
| Action 1.3 | [11 empty] | 0
| Action 1.4 | [11 empty] | 0
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 2.1 | [11 empty] | 0
| Action 2.2 | [11 empty] | 0
| Action 2.3 | [11 empty] | 0
| Action 2.4 | [11 empty] | 0
| Action 2.5 | [11 empty] | 0
| WP 3 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 3.1 | [11 empty] | 0
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 | [11 empty] | 0
| Action 4.4 | [11 empty] | 0
| Action 4.5 | [11 empty] | 0
| WP 5 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 5.1 | [11 empty] | 0
| Action 5.2 | [11 empty] | 0
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| P10 |  | Staff Costs |  | Overheads | Travel and accomodation | External Expertise & Services |  | Equipment | Investments / Infrastructure | Others |  | TOTALS
| WP 1 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 1.1 | [11 empty] | 0
| Action 1.2 | [11 empty] | 0
| Action 1.3 | [11 empty] | 0
| Action 1.4 | [11 empty] | 0
| Action 1.5 | [11 empty] | 0
| WP 2 |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 2.1 | [11 empty] | 0
| Action 2.2 | [11 empty] | 0
| Action 2.3 | [11 empty] | 0
| Action 2.4 | [11 empty] | 0
| Action 2.5 | [11 empty] | 0
| WP 3 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 3.1 | [11 empty] | 0
| Action 3.2 | [11 empty] | 0
| Action 3.3 | [11 empty] | 0
| Action 3.4 | [11 empty] | 0
| Action 3.5 | [11 empty] | 0
| WP 4 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 4.1 | [11 empty] | 0
| Action 4.2 | [11 empty] | 0
| Action 4.3 | [11 empty] | 0
| Action 4.4 | [11 empty] | 0
| Action 4.5 | [11 empty] | 0
| WP 5 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 5.1 | [11 empty] | 0
| Action 5.2 | [11 empty] | 0
| Action 5.3 | [11 empty] | 0
| Action 5.4 | [11 empty] | 0
| Action 5.5 | [11 empty] | 0
| WP 6 | Title | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
| Action 6.1 | [11 empty] | 0
| Action 6.2 | [11 empty] | 0
| Action 6.3 | [11 empty] | 0
| Action 6.4 | [11 empty] | 0
| Action 6.5 | [11 empty] | 0
| TOTALS |  | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0
Costs per Deliverable and Partner
| Action No | Deliv. No |  | Deliverable Title |  |  | Partner No | Partner Contribution to Deliverable |  |  |  | Costs (in EUR)
| 1.1 | 1.1.1 |  | Project proposal |  |  | LP | LP collected all relevant information from the partners and prepared the project proposal |  |  |  | 3000
| 1.2 | 1.2.1 |  | Interim and the Final report (Technical & Financial reports) |  |  | LP | LP collects all relevant information from partners regarding technical and financial progress and prepares the reports |  |  |  | 10000
| 1.3 | 1.3.1 |  | 8 Progress Reports |  |  | LP | LP collects all relevant information from partners regarding financial progress and prepares the reports |  |  |  | 39900
| 1.4 | 1.4.1 |  | Minutes from Kick off and partner's meetings |  |  | LP | LP organizes the Kick off meeting, 1 partner meeting in Greece and prepares the minutes |  |  |  | 8455
| 1.4 | 1.4.8 |  | Closeout meeting (minutes, report & follow-up report) |  |  | LP | LP organizes the closeout meeting in Greece and prepares the minutes |  |  |  | 1850
| 2.1 | 2.1.1 |  | Communication plan |  |  | LP | LP prepares a communication plan for the dissemination of the proposed technology |  |  |  | 1400
| 2.3 | 2.3.1 |  | Publicity Material (website, TV spots, Radio spots) |  |  | LP | LP develops or upgrades a website . |  |  |  | 5600
| 2.4 | 2.4.1 |  | Newspaper entries |  |  | LP | LP publishes 4 newspaper entries to disseminate the produced results |  |  |  | 2000
| 2.5 | 2.5.1 |  | Conference presentations & proceedings |  |  | LP | LP in collaboration with P2 organizes a conference in the Achaia region |  |  |  | 5700
| 2.5 | 2.5.2 |  | Conference presentations & proceedings |  |  | LP | LP participates in a conference in Italy in Bari region organized by P6 |  |  |  | 3245
| 2.5 | 2.5.3 |  | Conference presentations & proceedings |  |  | LP | LP participates in an International (WasteEng12 or VENICE 2012) and a National conference (PRE-XI or CEST2013) |  |  |  | 7170
| 3.1 | 3.1.1 |  | Physicochemical characteristics of biogas boosting wastes |  |  | LP | LP runs chemical and biological analysis of agro-waste samples provided by each partner. |  |  |  | 8910
| 3.2 | 3.2.1 |  | Supporting laboratory equipment |  |  | LP | Laboratory Equipment is commissioned by LP to support the operation of pilot plants through continuous monitoring |  |  |  | 187500
| 3.3 | 3.3.1 |  | Technical Report with lab-scale experimental results and model predictions |  |  | LP | LP runs laboratory experiments to test the efficiency of partners' agrowastes and studies the treatment of anaerobic effluent. |  |  |  | 34000
| 3.4 | 3.4.1 |  | Technical Report with results from anaerobic effluent post treatment |  |  | LP | LP runs laboratory experiments for identification of best combination of anaerobic effluent post treatment |  |  |  | 20100
| 4.1 | 4.1.1 |  | Technical specifications for pilot plant commissioning |  |  | LP | LP prepares the technical specificatios for the Italian pilot plant commissioning and supervises the proper construction of Italian pilot plant |  |  |  | 5770
| 4.3 | 4.3.1 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance |  |  | LP | LP is scientifically responsible for the operation of both Greek and Italian pilot plants for the Implementation of Greek & Italian mixtures for advanced biogas performance |  |  |  | 29350
| 4.4 | 4.4.1 |  | Technical Report with pilot scale results from anaerobic effluent post treatment |  |  | LP | LP is scientifically responsible for the implementation of best post treatment anaerobic effluent methodology on Greek & Italian pilot plants |  |  |  | 8400
| 4.5 | 4.5.1 |  | Technical Report with Greek & Italian sludges composting results |  |  | LP | LP is responsible for the composting of sludges from the operation of Greek & Italian pilot plants |  |  |  | 17650
| 5.1 | 5.1.1 |  | Technoeconomic Evaluation |  |  | LP | LP selects the best waste mixture scenarios in each partner region that maximize overall system performance based on technoeconomic evaluations of obtained results |  |  |  | 5000
| 5.2 | 5.2.1 |  | Expoitation plan |  |  | LP | LP evaluates pilot-scale results, selects the best mixtures for each partner and provides an example of exploitation plan. |  |  |  | 5000
| 1.1 | 1.1.2 |  | Project proposal |  |  | P2 | P2 provided all requested information to LP and collaborated in the preparation of the project proposal |  |  |  | 0
| 1.2 | 1.2.2 |  | Interim and the Final report (Technical & Financial reports) |  |  | P2 | P2 provides all technical and financial information to LP for the preparation of the reports |  |  |  | 7000
| 1.3 | 1.3.2 |  | 8 Progress Reports |  |  | P2 | P2 provides all financial information to LP for the preparation of the reports |  |  |  | 14250
| 1.4 | 1.4.2 |  | Minutes from partners meeting |  |  | P2 | P2 will participate in 3 Progress/Evaluation Meetings organised by the partners |  |  |  | 5830
| 2.1 | 2.1.2 |  | Communication plan |  |  | P2 | P2 prepares a communication plan for the dissemination of the proposed technology |  |  |  | 3000
| 2.2 | 2.2.1 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) |  |  | P2 | P2 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services |  |  |  | 7500
| 2.3 | 2.3.2 |  | Website updated during the whole project |  |  | P2 | P2 contributes to the website upgrading |  |  |  | 4500
| 2.4 | 2.4.2 |  | Publicity Material (TV spots, Radio spots, newspaper entries) |  |  | P2 | P2 produces 2 TV Spots, 1 Radio Spot and prepares 4 entries in the local newspapers. |  |  |  | 7985
| 2.5 | 2.5.4 |  | Conference presentations & proceedings |  |  | P2 | P2 in collaboration with LP organizes a conference in the Achaia region and participates in a conference in Italy (Bari region) organised by P6. |  |  |  | 14220
| 3.1 | 3.1.2 |  | Technical report on estimated amounts of agro-wastes |  |  | P2 | P2 runs a survey to determine the types and amounts of agrowaste residuals in the Prefecture of Achaia |  |  |  | 11200
| 4.3 | 4.3.2 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance |  |  | P2 | P2 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production |  |  |  | 15600
| 4.4 | 4.4.2 |  | Technical Report with pilot scale results from anaerobic effluent post treatment |  |  | P2 | P2 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P2's waste mixture |  |  |  | 5815
| 4.5 | 4.5.2 |  | Technical Report with Greek & Italian sludges composting results |  |  | P2 | P2 collaborates with LP in the composting of sludges from the operation of Greek pilot plant treating P2 waste mixture |  |  |  | 10600
| 5.1 | 5.1.2 |  | Technoeconomic evaluation |  |  | P2 | P2 will conduct a study based on the indicative results from LP for the whole Achaia Prefecture. |  |  |  | 2500
| 5.2 | 5.2.2 |  | Exploitation plan |  |  | P2 | P2 will conduct a study based on the indicative results from LP for the former Prefecture of Achaia |  |  |  | 25000
| 1.1 | 1.1.3 |  | Project proposal |  |  | P3 | P3 provided all requested information to LP and collaborated in the preparation of the project proposal |  |  |  | 2500
| 1.2 | 1.2.3 |  | Interim and the Final report (Technical & Financial reports) |  |  | P3 | P3 provides all technical and financial information to LP for the preparation of the reports |  |  |  | 4500
| 1.3 | 1.3.3 |  | 8 Progress Reports |  |  | P3 | P3 provides all financial information to LP for the preparation of the reports |  |  |  | 4000
| 1.4 | 1.4.3 |  | Minutes from partners meeting |  |  | P3 | P3 will participate in 3 Progress/Evaluation Meetings organised by the partners |  |  |  | 5830
| 2.1 | 2.1.3 |  | Communication plan |  |  | P3 | P3 prepares a communication plan for the dissemination of the proposed technology |  |  |  | 5000
| 2.2 | 2.2.2 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) |  |  | P3 | P3 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services |  |  |  | 6500
| 2.3 | 2.3.3 |  | Website updated during the whole project |  |  | P3 | P3 contributes to the website upgrading |  |  |  | 2000
| 2.4 | 2.4.3 |  | Publicity Material (TV spots, Radio spots, newspaper entries) |  |  | P3 | P3 produces 1 TV Spot and prepares 4 entries in the local newspapers. |  |  |  | 5970
| 2.5 | 2.5.5 |  | Conference presentations & proceedings |  |  | P3 | P3 organizes a conference in the Aitoloakarnania region for the dissemination of its results. |  |  |  | 13125
| 2.5 | 2.5.6 |  | Conference presentations & proceedings |  |  | P3 | P3 participates in a conference in Italy (Bari region) organised by P6. |  |  |  | 3220
| 3.1 | 3.1.3 |  | Technical report on estimated amounts of agro-wastes |  |  | P3 | P3 runs a survey to determine the types and amounts of agrowaste residuals in the former Prefecture of Etoloakarnania |  |  |  | 10300
| 4.3 | 4.3.3 |  | Technical Report with Greek & Italian pilot plant operational results |  |  | P3 | P3 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production |  |  |  | 9355
| 4.4 | 4.4.3 |  | Technical Report with pilot scale results from anaerobic effluent post treatment |  |  | P3 | P3 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P3's waste mixture |  |  |  | 7900
| 4.5 | 4.5.3 |  | Technical Report with Greek & Italian sludges composting results |  |  | P3 | P3 is responsible for the composting of sludges from the operation of Greek & Italian pilot plants |  |  |  | 5300
| 5.1 | 5.1.3 |  | Technoeconomic evaluation |  |  | P3 | P3 will conduct a study based on the indicative results from LP for the former Prefecture of Etoloakarnania |  |  |  | 8000
| 5.2 | 5.2.3 |  | Exploitation plan |  |  | P3 | P3 will conduct a study based on the indicative results from LP for the former Prefecture of Etoloakarnania |  |  |  | 21500
| 1.1 | 1.1.4 |  | Project proposal |  |  | P4 | P4 provided all requested information to LP and collaborated in the preparation of the project proposal |  |  |  | 0
| 1.2 | 1.2.4 |  | Interim and the Final report (Technical & Financial reports) |  |  | P4 | P4 provides all technical and financial information to LP for the preparation of the reports |  |  |  | 12695
| 1.3 | 1.3.4 |  | 8 Progress Reports |  |  | P4 | P4 provides all financial information to LP for the preparation of the reports |  |  |  | 14370
| 1.4 | 1.4.4 |  | Minutes from partners meeting |  |  | P4 | P4 will participate in 3 Progress/Evaluation Meetings organised by the partners |  |  |  | 11860
| 2.1 | 2.1.4 |  | Communication plan |  |  | P4 | P4 prepares a communication plan for the dissemination of the proposed technology |  |  |  | 4000
| 2.2 | 2.2.3 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) |  |  | P4 | P4 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services |  |  |  | 11000
| 2.3 | 2.3.4 |  | Website updated during the whole project |  |  | P4 | P4 contributes to the website upgrading |  |  |  | 4000
| 2.4 | 2.4.4 |  | Publicity Material (TV spots, Radio spots, newspaper entries) |  |  | P4 | P4 produces 2 TV Spots, 2 Radio Spot and prepares 8 entries in the local newspapers. |  |  |  | 14000
| 2.5 | 2.5.7 |  | Conference presentations & proceedings |  |  | P4 | P4 participates in a conference in Italy (Bari region) organised by P6 |  |  |  | 3620
| 2.5 | 2.5.8 |  | Conference presentations & proceedings |  |  | P4 | P4 organizes 2 conferences in the Region of Epirus - Former Prefecture of Preveza and Arta for the dissemination of its results. |  |  |  | 9000
| 3.1 | 3.1.4 |  | Technical report on estimated amounts of agro-wastes |  |  | P4 | P4 runs a survey to determine the types and amounts of agrowaste residuals in the Region of Epirus - Former Prefecture of Preveza and Arta |  |  |  | 15800
| 4.3 | 4.3.4 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance |  |  | P4 | P4 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production |  |  |  | 19655
| 4.4 | 4.4.4 |  | Technical Report with pilot scale results from anaerobic effluent post treatment |  |  | P4 | P4 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P4's waste mixture |  |  |  | 16000
| 4.5 | 4.5.4 |  | Technical Report with Greek & Italian sludges composting results |  |  | P4 | P4 collaborates with LP in the composting of sludge from the operation of Greek pilot plant treating P4's waste mixture |  |  |  | 15000
| 5.1 | 5.1.4 |  | Technoeconomic evaluation |  |  | P4 | P4 will conduct a study based on the indicative results from LP for the Region of Epirus - Former Prefectures of Preveza and Arta. |  |  |  | 1000
| 5.2 | 5.2.4 |  | Exploitation plan |  |  | P4 | P4 will conduct a study based on the indicative results from LP for the Region of Epirus - Former Prefectures of Preveza and Arta. |  |  |  | 34000
| 1.1 | 1.1.5 |  | Project proposal |  |  | P5 | P5 provided all requested information to LP and collaborated in the preparation of the project proposal |  |  |  | 0
| 1.2 | 1.2.5 |  | Interim and the Final report (Technical & Financial reports) |  |  | P5 | P5 provides all technical and financial information to LP for the preparation of the reports |  |  |  | 2000
| 1.3 | 1.3.5 |  | 8 Progress Reports |  |  | P5 | P5 provides all financial information to LP for the preparation of the reports |  |  |  | 17125
| 1.4 | 1.4.5 |  | Minutes from partners meeting |  |  | P5 | P5 will participate in 3 Progress/Evaluation Meetings organised by the partners |  |  |  | 4830
| 2.1 | 2.1.5 |  | Communication plan |  |  | P5 | P5 prepares a communication plan for the dissemination of the proposed technology |  |  |  | 5400
| 2.2 | 2.2.4 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) |  |  | P5 | P5 produces 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs using external services |  |  |  | 16000
| 2.3 | 2.3.5 |  | Website updated during the whole project |  |  | P5 | P5 contributes to the website upgrading |  |  |  | 2000
| 2.4 | 2.4.5 |  | Publicity Material (TV spots, Radio spots, newspaper entries) |  |  | P5 | P5 produces 1 TV Spots, 1 Radio Spot and prepares 4 entries in the local newspapers. |  |  |  | 10970
| 2.5 | 2.5.5 |  | Conference presentations & proceedings |  |  | P5 | P5 organizes a conference in the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki for the dissemination of its results. |  |  |  | 3220
| 2.5 | 2.5.9 |  | Conference presentations & proceedings |  |  | P5 | P5 participates in a conference in Italy (Bari) organised by P6 |  |  |  | 5000
| 3.1 | 3.1.5 |  | Technical report on estimated amounts of agro-wastes |  |  | P5 | P5 runs a survey to determine the types and amounts of agrowaste residuals in the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki |  |  |  | 6800
| 4.3 | 4.3.5 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance |  |  | P5 | P5 collaborates with LP in the operation of the Greek pilot plant. Various mixtures are tested for advanced biogas production |  |  |  | 10355
| 4.4 | 4.4.5 |  | Technical Report with pilot scale results from anaerobic effluent post treatment |  |  | P5 | P5 collaborates with LP in the operation of the Greek pilot plant. Implementation of best post treatment anaerobic effluent methodology on P5's waste mixture |  |  |  | 3500
| 4.5 | 4.5.5 |  | Technical Report with Greek & Italian sludges composting results |  |  | P5 | P5 collaborates with LP in the composting of sludge from the operation of Greek pilot plant treating P5's waste mixture |  |  |  | 5300
| 5.1 | 5.1.5 |  | Technoeconomic evaluation |  |  | P5 | P5 will conduct a study based on the indicative results from LP for the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki |  |  |  | 2500
| 5.2 | 5.2.5 |  | Exploitation plan |  |  | P5 | P5 will conduct a study based on the indicative results from LP for the Region of Ionian Islands - Former Perfecture of Kefallinia and Ithaki |  |  |  | 20000
| 1.1 | 1.1.6 |  | Project proposal |  |  | P6 | P6 provided all requested information to LP and collaborated in the preparation of the project proposal |  |  |  | 3000
| 1.2 | 1.2.6 |  | Interim and the Final report (Technical & Financial reports) |  |  | P6 | P6 provides all technical and financial information to LP for the preparation of the reports |  |  |  | 3000
| 1.3 | 1.3.6 |  | 8 Progress Reports |  |  | P6 | P6 provides all financial information to LP for the preparation of the reports |  |  |  | 3000
| 1.4 | 1.4.6 |  | Minutes from partners meeting |  |  | P6 | P6 will participate in 3 Progress/Evaluation Meetings organised by the partners |  |  |  | 9000
| 2.1 | 2.1.6 |  | Communication plan |  |  | P6 | P6 prepares a communication plan for the dissemination of the proposed technology |  |  |  | 3000
| 2.2 | 2.2.5 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) |  |  | P6 | P6 collaborates with P7 for the production of 3000 bilingual leaflets, 1000 posters, 4 Biannual newsletters and 1000 CDs |  |  |  | 3000
| 2.3 | 2.3.6 |  | Website updated during the whole project |  |  | P6 | P6 contributes to the website upgrading |  |  |  | 4000
| 2.5 | 2.5.10 |  | Conference presentations & proceedings |  |  | P6 | P6 organizes a conference in the Bari region for the dissemination of its results. |  |  |  | 5000
| 3.1 | 3.1.6 |  | Technical report on estimated amounts of agro-wastes |  |  | P6 | P6 runs a survey to determine the types and amounts of agrowaste residuals in the Province of Bari |  |  |  | 38250
| 4.1 | 4.1.2 |  | Italian pilot plant |  |  | P6 | Italian pilot plant is commissioned by P6 to evaluate enhanced biogas production from Italian agro-wastes |  |  |  | 223500
| 4.2 | 4.2.1 |  | Technical Report with Italian pilot plant operational results |  |  | P6 | P6 operates the Italian pilot plant. Various mixtures are tested. |  |  |  | 28750
| 4.3 | 4.3.6 |  | Technical Report with Greek & Italian pilot plant operational results for advanced performance |  |  | P6 | P6 collaborates with LP in the operation of the Italian pilot plant. Various mixtures are tested for advanced biogas production |  |  |  | 10000
| 4.4 | 4.4.6 |  | Technical Report with pilot scale results from anaerobic effluent post treatment |  |  | P6 | P6 collaborates with LP in the operation of the Italian pilot plant. Implementation of best post treatment anaerobic effluent methodology on P6's waste mixture |  |  |  | 11500
| 4.5 | 4.5.6 |  | Technical Report with Greek & Italian sludges composting results |  |  | P6 | P6 collaborates with LP in the composting of sludge from the operation of Italian pilot plant treating P6's waste mixture |  |  |  | 26000
| 5.1 | 5.1.6 |  | Technoeconomic evaluation |  |  | P6 | P6 will conduct a study based on the indicative results from LP for the whole Province of Bari. |  |  |  | 22000
| 5.2 | 5.2.6 |  | Exploitation plan |  |  | P6 | P6 will conduct a study based on the indicative results from LP for the whole Province of Bari. |  |  |  | 27000
| 1.1 | 1.1.7 |  | Project proposal |  |  | P7 | P7 provided all requested information to LP and collaborated in the preparation of the project proposal |  |  |  | 204
| 1.2 | 1.2.7 |  | Interim and the Final report (Technical & Financial reports) |  |  | P7 | P7 provides all technical and financial information to LP for the preparation of the reports |  |  |  | 918
| 1.3 | 1.3.7 |  | 8 Progress Reports |  |  | P7 | P7 provides all financial information to LP for the preparation of the reports |  |  |  | 1020
| 1.4 | 1.4.7 |  | Minutes from partners meeting |  |  | P7 | P7 will participate in 3 Progress/Evaluation Meetings organised by the partners |  |  |  | 4386
| 2.2 | 2.2.6 |  | Information Material (Brochures, Posters, Biannual newsletters, CD) |  |  | P7 | P7 produces 3000 bilingual leaflets and 1000 CDs using external services |  |  |  | 4037
| 2.3 | 2.3.7 |  | Website updated during the whole project |  |  | P7 | P7 contributes to the website upgrading |  |  |  | 612
| 2.4 | 2.4.6 |  | Publicity Material (TV spots, Radio spots, newspaper entries) |  |  | P7 | P7 produces 2 TV Spots, 1 Radio Spot and prepares 4 entries in the local newspapers. |  |  |  | 10863
| 2.5 | 2.5.11 |  | Conference presentations & proceedings |  |  | P7 | P7 organizes a conference in the Bari region for the dissemination of its results. |  |  |  | 2960
| 0 | 0 |  | 0 |  |  | 0 | 0
| 0 | 0 |  | 0 |  |  | 0 | 0
1406000

## Timetable
SECTION E - TIMETABLE
Timetable
|  | year | 2007 | [11 empty] | 2008 | [11 empty] | 2009 | [12 empty] | 2010 | [11 empty] | 2011 | [11 empty] | 2012 | [11 empty] | 2013 | [11 empty] | 2014 | [11 empty] | 2015
|  | month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 |  | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108
WP 1 | bar: 2011 59 to 2013 82
Action 1.1 | bar: 2010 37 to 2011 55
Action 1.2 | bar: 2011 59 to 2013 82
Action 1.3 | bar: 2011 59 to 2013 82
Action 1.4 | bar: 2011 59 to 2013 82
Action 1.5
WP 2 | bar: 2011 59 to 2013 82
Action 2.1 | bar: 2011 59
Action 2.2 | bar: 2013 78 to 2013 80
Action 2.3 | bar: 2011 60 to 2013 81
Action 2.4 | bar: 2012 70 to 2013 82
Action 2.5 | bar: 2013 76 to 2013 82
WP 3 | bar: 2011 59 to 2013 80
Action 3.1 | bar: 2011 59 to 2012 62
Action 3.2 | bar: 2011 59 to 2012 63
Action 3.3 | bar: 2012 61 to 2013 80
Action 3.4 | bar: 2012 64 to 2013 77
Action 3.5
WP 4 | bar: 2011 59 to 2013 80
Action 4.1 | bar: 2011 59 to 2012 63
Action 4.2 | bar: 2012 64 to 2012 72
Action 4.3 | bar: 2011 60 to 2013 80
Action 4.4 | bar: 2013 77 to 2013 80
Action 4.5 | bar: 2012 64 to 2013 80
WP 5 | bar: 2013 79 to 2013 81
Action 5.1 | bar: 2013 79 to 2013 80
Action 5.2 | bar: 2013 80 to 2013 81
Action 5.3
Action 5.4
Action 5.5
WP 6
Action 6.1
Action 6.2
Action 6.3
Action 6.4
Action 6.5
Budget per reporting period
|  |  | 2009 | [11 empty] | 2010 | [11 empty] | 2011 | [12 empty] | 2010 37: 2012; 2011 49: 2013; 2012 62: 2014; 2013 74: 2015; 2014 86: TOTALS
|  |  | RP 1 |  |  | RP 2 |  |  | RP 3 |  |  | RP 4 |  |  | RP 1 |  |  | RP 2 |  |  | RP 3 |  |  | RP 4 |  |  | RP1 |  | RP2 | RP2 |  | RP3 | RP3 |  | RP4 | RP4 |  |  | RP 1 | 2010 40: RP2; 2010 43: RP3; 2010 46: RP4; 2011 49: RP1; 2011 52: RP2; 2011 55: RP3; 2011 58: RP4; 2012 62: RP1; 2012 65: RP2; 2012 68: RP3; 2012 71: RP4; 2013 74: RP1; 2013 77: RP2; 2013 80: RP3; 2013 83: RP4
| WP 1 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 32860.6786 |  |  |  | 2010 37: 24156.6786; 2010 40: 24156.6786; 2010 43: 16722.25; 2010 46: 24156.6786; 2011 49: 24156.6786; 2011 52: 24156.6786; 2011 55: 24156.6786; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 194523
| Action 1.1 | [34 empty] | 8704 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 0; 2014 86: 8704
| Action 1.2 | [34 empty] | 5014.125 |  |  |  | 2010 37: 5014.125; 2010 40: 5014.125; 2010 43: 5014.125; 2010 46: 5014.125; 2011 49: 5014.125; 2011 52: 5014.125; 2011 55: 5014.125; 2014 86: 40113
| Action 1.3 | [34 empty] | 11708.125 |  |  |  | 2010 37: 11708.125; 2010 40: 11708.125; 2010 43: 11708.125; 2010 46: 11708.125; 2011 49: 11708.125; 2011 52: 11708.125; 2011 55: 11708.125; 2014 86: 93665
| Action 1.4 | [34 empty] | 7434.4286 |  |  |  | 2010 37: 7434.4286; 2010 40: 7434.4286; 2010 43: 0; 2010 46: 7434.4286; 2011 49: 7434.4286; 2011 52: 7434.4286; 2011 55: 7434.4286; 2014 86: 52041
| Action 1.5 | [38 empty] | 2014 86: 0
| WP 2 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 27478 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 18625; 2010 46: 0; 2011 49: 37495; 2011 52: 79854; 2011 55: 56365; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 219817
| Action 2.1 | [34 empty] | 21800 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 0; 2014 86: 21800
| Action 2.2 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 48037; 2011 55: 0; 2014 86: 48037
| Action 2.3 | [34 empty] | 5678 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 5678; 2010 46: 0; 2011 49: 5678; 2011 52: 0; 2011 55: 5678; 2014 86: 22712
| Action 2.4 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 12947; 2010 46: 0; 2011 49: 12947; 2011 52: 12947; 2011 55: 12947; 2014 86: 51788
| Action 2.5 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 18870; 2011 52: 18870; 2011 55: 37740; 2014 86: 75480
| WP 3 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 70945 |  |  |  | 2010 37: 212672.1429; 2010 40: 8877.1429; 2010 43: 8877.1429; 2010 46: 8877.1429; 2011 49: 8877.1429; 2011 52: 8877.1429; 2011 55: 4857.1429; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 332860
| Action 3.1 | [34 empty] | 68445 |  |  |  | 2010 37: 22815; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 0; 2014 86: 91260
| Action 3.2 | [34 empty] | 2500 |  |  |  | 2010 37: 185000; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 0; 2014 86: 187500
| Action 3.3 | [34 empty] | 0 |  |  |  | 2010 37: 4857.1429; 2010 40: 4857.1429; 2010 43: 4857.1429; 2010 46: 4857.1429; 2011 49: 4857.1429; 2011 52: 4857.1429; 2011 55: 4857.1429; 2014 86: 34000
| Action 3.4 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 4020; 2010 43: 4020; 2010 46: 4020; 2011 49: 4020; 2011 52: 4020; 2011 55: 0; 2014 86: 20100
| Action 3.5 | [38 empty] | 2014 86: 0
| WP 4 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 30500 |  |  |  | 2010 37: 223055; 2010 40: 39632.5; 2010 43: 46132.5; 2010 46: 37299.1667; 2011 49: 38147.5; 2011 52: 56025; 2011 55: 14508.3333; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 485300
| Action 4.1 | [34 empty] | 22500 |  |  |  | 2010 37: 206770; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 0; 2014 86: 229270
| Action 4.2 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 7187.5; 2010 43: 7187.5; 2010 46: 7187.5; 2011 49: 7187.5; 2011 52: 0; 2011 55: 0; 2014 86: 28750
| Action 4.3 | [34 empty] | 8000 |  |  |  | 2010 37: 10985; 2010 40: 19203.3333; 2010 43: 19203.3333; 2010 46: 15670; 2011 49: 9118.3333; 2011 52: 9118.3333; 2011 55: 3016.6667; 2014 86: 94315
| Action 4.4 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 9750; 2011 52: 34815; 2011 55: 8550; 2014 86: 53115
| Action 4.5 | [34 empty] | 0 |  |  |  | 2010 37: 5300; 2010 40: 13241.6667; 2010 43: 19741.6667; 2010 46: 14441.6667; 2011 49: 12091.6667; 2011 52: 12091.6667; 2011 55: 2941.6667; 2014 86: 79850
| WP 5 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 13666.6667; 2011 55: 159833.3333; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 173500
| Action 5.1 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 13666.6667; 2011 55: 27333.3333; 2014 86: 41000
| Action 5.2 | [34 empty] | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 132500; 2014 86: 132500
| Action 5.3 | [38 empty] | 2014 86: 0
| Action 5.4 | [38 empty] | 2014 86: 0
| Action 5.5 | [38 empty] | 2014 86: 0
| WP 6 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  |  | 2010 37: 0; 2010 40: 0; 2010 43: 0; 2010 46: 0; 2011 49: 0; 2011 52: 0; 2011 55: 0; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 0
| Action 6.1 | [38 empty] | 2014 86: 0
| Action 6.2 | [38 empty] | 2014 86: 0
| Action 6.3 | [38 empty] | 2014 86: 0
| Action 6.4 | [38 empty] | 2014 86: 0
| Action 6.5 | [38 empty] | 2014 86: 0
|  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 161783.6786 |  |  | 161783.6786 | 2010 37: 459883.8214; 2010 40: 72666.3214; 2010 43: 90356.8929; 2010 46: 70332.9881; 2011 49: 108676.3214; 2011 52: 182579.4881; 2011 55: 259720.4881; 2011 58: 0; 2012 62: 0; 2012 65: 0; 2012 68: 0; 2012 71: 0; 2013 74: 0; 2013 77: 0; 2013 80: 0; 2013 83: 0; 2014 86: 1406000

## Indicators
SECTION F - INDICATORS
| Priority Axis | 3. Improving the quality of life, protection of the environment and enhancement of social and cultural cohesion
| Specific Objective | 3.2. Valorisation & improvement of joint protection, management of natural resources, natural and technological risks’ prevention
OUTPUT INDICATORS
| Indicators |  | Unit of Measurement | Target
| Interventions to encourage and improve the joint protection and management of the natural environment and water resources |  | Number | 6
| Number of joint actions for risk prevention and natural hazard projects |  | Number | 1
| Number of research projects and / or relative actions that contribute to the improvement of the quality of Life and have an environmental added value |  | Number | 1
| Interventions for the protection of Natura Areas |  | Number
| Number of projects concerning solid waste management |  | Number | 1
RESULT INDICATORS
|  |  | Unit of Measurement | Target
| Number of people that benefit from projects related to wastewater management, water quality, risk prevention and public services |  | Number | 2200000

## Check List for Submission
SECTION G - CHECK LIST FOR SUBMISSION
Please make sure that you have fulfilled the requirements listed below before submitting the documents.
|  | x | The paper version of the Project Proposal (comprising the completed Application Form and all the required documents demanded by the Call) are submitted to the JTS within the deadline, as defined in the Call for Proposals.
|  | x | The correct Application Form and Annexes provided in this Call for Proposals have been used.
|  | x | 1 original of the Project Proposal is included in one single package / envelope.
|  | x | The electronic version of the completed Application Form, the Sustainability Document and the Justification of the Budget are submitted on a CD-ROM or DVD-ROM.
|  | x | The electronic and paper versions of the Application Form, the Sustainability Document and the Justification of the Budget are identical.
|  | x | The Application Form and all the documents provided as templates by the MA are submitted in the working language of the programme (English).
|  | x | The Application form, the Sustainability Document and the Justification of the Budget are dated, signed and stamped by the Lead Partner.
|  | x | All Partners participating in the project are listed in section C of the Application Form with their institution’s name in original and English language.
|  | x | Annexed to the Application Form are: 1) The Partnership Declaration (standard form provided) signed and stamped by all Partners including the Lead Partner, 2) The Declaration of not generating revenues (standard form provided) signed by the Lead Partner, 3) The Justification of the Budget Costs (standard form provided), 4) Documentation required according to the Call for Proposals for infrastructure projects, if relevant ( building permits, a compliance assessment report, preliminary studies, technical designs or any of the relevant technical documentation, actual Bill of Cost and Quantities, document certifying the ownership of land/building or documentation transferring the operation rights for the period of 5 years after the end of the project, environmental impact assessments etc.), 5) For Bodies governed by public law, official documents proving that they meet this Call's requirements, 6) For private organizations, documents for establishing the applicant's entity, official documentation
indicating the sources of the body's revenues, a declaration for the non-distribution of profits and official documentation proving that the organization operates at least 1 year before the launch of the specific Call, 7)A maximum 2-page document justifying the financial and operational sustainability of the project outcomes after the end
of the financing period.
|  | x | The duration of the proposed project is in line with the requirements of the Call for Proposals.
|  | x | The budget of the proposed project is inside the limits set by the Call for Proposals.
|  | x | The Budget in all the requested Documents is expressed in Euros (€).

## VF (hidden)
1. Strengthening competitiveness and innovation | 1.1. Strengthening interaction between research/innovation institutions, SMEs and public authorities
2. Improve accessibility to sustainable networks and services | 1.2. Promoting cross-border advanced new technologies
3. Improving the quality of life, protection of the environment and enhancement of social and cultural cohesion | 2.1. Enhancement of the cross-border integrated and sustainable connections
4. Technical support for implementation | 2.2. Improvement of transport, information and communication networks and services
3.1. Promotion of cultural and natural heritage
3.2. Valorisation & improvement of joint protection, management of natural resources, natural and technological risks’ prevention
3.3. Protection of health and promotion of social integration
4.1. Support to the management, monitoring, implementation and audit of the programme’s operations
4.2. Support for the broad publicity and information of the programme
GREECE | Prefecture of Aitoloakarnania
ITALY | Prefecture of Achaia
Prefecture of Kerkyra/Corfu
Prefecture of Lefkada
Prefecture of Kefallinia/Cephalonia
Prefecture of Zakynthos
Prefecture of Ioannina
Prefecture of Preveza
Prefecture of Thesprotia
Prefecture of Ilia
Prefecture of Arta
Province of Bari
Province of Brindisi
Province of Lecce
Province of Taranto
Province of Foggia
1.1
1.2
1.3
1.4
1.5
2.1
2.2
2.3
LP | 2.4
P2 | 2.5
P3 | 3.1
P4 | 3.2
P5 | 3.3
P6 | 3.4
P7 | 3.5
P8 | 4.1
P9 | 4.2
P10 | 4.3
4.4
4.5
5.1
5.2
5.3
5.4
public | 5.5
governed by public law | 6.1
private organization | 6.2
6.3
6.4
6.5
eligible
not-eligible
Output Indicators 1.1
Number of systemic innovation actions which contribute to increase the competitiveness of the cross border economic systems
Number of bilateral or international research projects on innovation and competitiveness of the cross border economic systems carried out by Universities and research institutes
Number of actions concerning SMEs cooperation and/or SMEs joint actions for internationalisation in the maritime border region
Number of SMEs involved in R&D activities and networks
Result Indicators 1.1
Output Indicators 1.2
Number of actions concerning SMEs support for ICT modernisation
Number of SMEs that have promoted innovation by environmental friendly solutions
Number of research projects and / or relative actions that contribute to the improvement of the quality of Life and have an environmental added value
Result Indicators 1.2
Number of women and youngsters in new mid-term occupation by competitive actions
Percentage of SMEs funded by the CBC for ICT modernisation which are able to perform e-commerce activities (accept electronic orders or execute electronic sales)
Output Indicators 2.1
Number of actions promoted for the development / improvement of smart transport systems in the programme area
Number of projects that contribute to the improvement of sustainability and attractiveness of Urban Environment
Result Indicators 2.1
Joint strategies and interventions developed in the fields of local, inter-modal and cross board transport systems
Interventions concerning infrastructures, transport systems, transport and information networks management
Output Indicators 2.2
Number of actions promoted for the modernization of control and transport security services
Number of projects that contribute to the improvement of sustainability and attractiveness of Urban Environment
Result Indicators 2.2
Number of joint partnerships and networks established in the framework of the Priority Axis
Number of citizens inside the cross-borderregions who will benefit from the new accessibility infrastructure and actions
Output Indicators 3.1
Number of joint events and cooperation in the fields of tourism, culture and natural heritage promotion
Number of research projects and / or relative actions that contribute to the improvement of the quality of Life and have an environmental added value
Interventions for the protection of Natura Areas
Number of projects concerning solid waste management
Result Indicators 3.1
Percentage of tourism increase in the programming area
Output Indicators 3.2
Interventions to encourage and improve the joint protection and management of the natural environment and water resources
Number of joint actions for risk prevention and natural hazard projects
Number of research projects and / or relative actions that contribute to the improvement of the quality of Life and have an environmental added value
Interventions for the protection of Natura Areas
Number of projects concerning solid waste management
Result Indicators 3.2
Number of people that benefit from projects related to wastewater management, water quality, risk prevention and public services
Output Indicators 3.3
Number of joint actions for the protection of health and the promotion social integration
Number of research projects and / or relative actions that contribute to the improvement of the quality of Life and have an environmental added value
Interventions for the protection of Natura Areas
Number of projects concerning solid waste management
Result Indicators 3.3
Number of people that benefit from projects for better health and social public services
Measurment 1.1
Number
Number
Number
Number
Measurment 1.2
Number
Number
Number
Measurment 2.1
Number
Number
Measurment 2.2
Number
Number
Measurment 3.1
Number
Number
Number
Number
Measurment 3.2
Number
Number
Number
Number
Number
Measurment 3.3
Number
Number
Number
Number
MeasurmentR 1.1
MeasurmentR 1.2
Number
%
MeasurmentR 2.1
Number
Number
MeasurmentR 2.2
Number
Number
MeasurmentR 3.1
%
MeasurmentR 3.2
Number
MeasurmentR 3.3
Number

## TM_PART_D2_Budget (hidden)
Left | Top | Right | Bottom | Ref